## Gantt Chart
GANTT CHART |  |  | Or, Click Here to Create a Collaborative Gantt Chart with
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter | Leon W | 2017-03-12 | 2017-03-15 | 4 | 100% | bar: WEEK 1 F to WEEK 2 F
1.1.1 | Project Charter Revisions | Kylie R | 2017-03-15 | 2017-03-16 | 2 | 100% | bar: WEEK 2 W to WEEK 2 F
1.2 | Research | Pete S | 2017-03-15 | 2017-03-21 | 7 | 90% | bar: WEEK 2 W to WEEK 3 R
1.3 | Projections | Steve L | 2017-03-16 | 2017-03-22 | 7 | 40% | bar: WEEK 2 W to WEEK 3 R
1.4 | Stakeholders | Allen W | 2017-03-17 | 2017-03-22 | 7 | 70% | bar: WEEK 2 W to WEEK 3 R
1.5 | Guidelines | Malik M | 2017-03-18 | 2017-03-22 | 7 | 60% | bar: WEEK 2 W to WEEK 3 R
1.6 | Project Initiation | Malik M | 2017-03-23 | 2017-03-23 | 1 | 50% | bar: WEEK 2 W to WEEK 2 F; WEEK 3 F
2 | Project Definition and Planning
2.1 | Scope & Goal Setting | Steve L | 2017-03-24 | 2017-03-28 | 5 | 5% | bar: WEEK 2 W to WEEK 2 F; WEEK 4 M to WEEK 4 F
2.2 | Budget | Allen W | 2017-03-29 | 2017-04-02 | 5 | 30% | bar: WEEK 2 W to WEEK 2 F
2.3 | Communication Plan | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
2.4 | Risk Management | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3 | Project Launch and Execution
3.1 | Status & Tracking | Pete S |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.2 | KPIs | Leon W |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.2.1 | Monitoring | Kylie R |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.2.2 | Forecasts | Kylie R |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.3 | Project Updates | Pete S |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
3.3.1 | Chart Updates | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4.2 | Quality Deliverables | Allen W |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4.3 | Effort and Cost Tracking | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
4.4 | Project Performance | Malik M |  |  |  | 0% | bar: WEEK 2 W to WEEK 2 F
Or, Click Here to Create a Collaborative Gantt Chart with Smartsheet

## Gantt Chart BLANK
GANTT CHART | [6 empty] | Or, Click Here to Create a Collaborative Gantt Chart with
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1
1.1
Or, Click Here to Create a Gantt Chart with Smartsheet