{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Software Migration Plan"],"not_rendered":{"charts":1,"images":2,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Software Migration Plan","index":0,"n_rows":28,"n_cols":7,"rows_kept":28,"cut":false,"hidden":false,"merged":[[27,3,27,9],[2,1,2,6]]}
[null,"SOFTWARE MIGRATION PLAN TEMPLATE"]
[]
[null,"Project Name"]
[null,"TASK NAME","START","END","DURATION (days)","TASK OWNER","PERCENT OF \nTASK COMPLETE"]
[null,"PHASE 1 – SELF-ASSESSMENT"]
[null,"Define business vision","2018-09-02","2018-09-02",{"$f":"D6-C6+1","v":1},null,1]
[null,"Identify skills","2018-09-03","2018-09-03",{"$f":"D7-C7+1","v":1},null,1]
[null,"Decide whether to proceed","2018-09-04","2018-09-04",{"$f":"D8-C8+1","v":1},null,1]
[null,"PHASE 1 – DEFINE OPPORTUNITY"]
[null,"Research market","2018-09-05","2018-09-05",{"$f":"D10-C10+1","v":1},null,0.33]
[null,"Conduct interviews","2018-09-06","2018-09-10",{"$f":"D11-C11+1","v":5},null,0.7]
[null,"Identify needed resources","2018-09-11","2018-09-13",{"$f":"D12-C12+1","v":3},null,0.22]
[null,"Identify operating costs","2018-09-13","2018-09-14",{"$f":"D13-C13+1","v":2},null,0.4]
[null,"PHASE 1 – EVALUATE POTENTIAL RISKS"]
[null,"Assess market size","2018-09-15","2018-09-17",{"$f":"D15-C15+1","v":3},null,0.6]
[null,"Estimate competition","2018-09-17","2018-09-18",2,null,0]
[null,"Assess needed resources","2018-09-18","2018-09-19",2,null,0]
[null,"Determine financial requirements","2018-09-19","2018-09-21",3,null,0]
[null,"Evaluate profitability","2018-09-21","2018-09-22",2,null,0]
[null,"Review strategy","2018-09-22","2018-09-23",2,null,0.25]
[null,"PHASE 2 – DEFINE MARKET"]
[null,"Access available research","2018-09-23","2018-09-25",{"$f":"D22-C22+1","v":3},null,0.4]
[null,"Create market analysis","2018-09-26","2018-09-29",{"$f":"D23-C23+1","v":4},null,0.25]
[null,"Implement market analysis","2018-09-29","2018-10-01",{"$f":"D24-C24+1","v":3},null,0.33]
[]
[]
[]
[null,null,null,"CLICK HERE TO CREATE SOFTWARE MIGRATION PLAN TEMPLATES IN SMARTSHEET"]