{"text_format":"1","workbook":"xlsx","n_sheets":3,"sheets":["T. de b. de gestion de projets","Sheet1","Données liées au projet"],"not_rendered":{"charts":8,"images":1,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"T. de b. de gestion de projets","index":0,"n_rows":171,"n_cols":10,"rows_kept":171,"cut":false,"hidden":false,"merged":[[155,9,155,13],[156,9,156,13],[157,9,157,13],[158,9,158,13],[159,9,159,13],[170,0,174,13],[159,0,159,2],[160,0,160,2],[161,0,161,2],[162,0,162,2],[163,0,163,2],[168,0,168,2],[160,9,160,13],[161,9,161,13],[162,9,162,13],[163,9,163,13],[164,9,164,13],[165,9,165,13],[166,9,166,13],[167,9,167,13],[168,9,168,13],[164,0,164,2],[165,0,165,2],[166,0,166,2],[167,0,167,2],[0,0,0,8],[1,0,1,13],[46,0,46,13],[72,0,72,13],[152,0,152,13],[112,0,112,13],[154,0,154,2],[155,0,155,2],[156,0,156,2],[157,0,157,2],[158,0,158,2],[154,9,154,13]]}
["TABLEAU DE BORD DE GESTION DE PROJETS"]
["CALENDRIER DES TÂCHES"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["BUDGET DU PROJET"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["ANALYSE DES RISQUES"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["PROBLÈMES À RÉSOUDRE ET ACTIONS EN COURS"]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
[]
["RAPPORT SUR LE PROJET"]
[]
["TÂCHE",null,null,"RESPONSABLE","ÉCHÉANCE","BUDGET","RESSOURCES","RISQUES","PROBLÈMES","COMMENTAIRES"]
["Démarrage du projet",null,null,"Anna"]
["Définition des objectifs",null,null,"Ken"]
["Définition des besoins du projet",null,null,"Sara"]
["Définition des besoins matériels",null,null,"James"]
["Plannification des ressources finalisée",null,null,"Anna"]
["Exposé aux investisseurs",null,null,"Ken"]
["Recrutement du personnel",null,null,"Sara"]
["Réalisation",null,null,"James"]
["Version alpha prête",null,null,"Pete"]
["Tests alpha",null,null,"Jason"]
["Version bêta prête",null,null,"Pete"]
["Tests bêta",null,null,"Jason"]
["Lancement",null,null,"Pete"]
["Plannification à venir",null,null,"Anna"]
[]
["En savoir plus sur les tableaux de bord dans Smartsheet"]

{"sheet":"Sheet1","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[]}

{"sheet":"Données liées au projet","index":2,"n_rows":37,"n_cols":10,"rows_kept":37,"cut":false,"hidden":false,"merged":[[0,0,0,10],[1,7,1,9],[9,7,10,9],[19,0,19,6],[20,1,20,3],[20,4,20,5],[20,6,21,6],[20,0,21,0],[1,0,1,5]]}
["DONNÉES LIÉES AU PROJET"]
["LISTE DES TÂCHES ET CALENDRIER",null,null,null,null,null,null,"STATUT DES TÂCHES"]
["TÂCHES","RESPONSABLE","DÉBUT","FIN","NO. DE JOURS","STATUT",null,"STATUT","NOMBRE","%"]
["Démarrage du projet","Anna","2016-05-05","2016-05-06",{"$f":"D4-C4","v":1},"TERMINÉ",null,"TERMINÉ",4,{"$f":"I4/SUM(I4:I7)","v":0.2857142857142857}]
["Définition des objectifs","Ken","2016-05-07","2016-05-12",{"$f":"D5-C5","v":5},"TERMINÉ",null,"EN RETARD",2,{"$f":"I5/SUM(I4:I7)","v":0.14285714285714285}]
["Définition des besoins du projet","Sara","2016-05-13","2016-05-20",7,"TERMINÉ",null,"EN COURS",2,{"$f":"I6/SUM(I4:I7)","v":0.14285714285714285}]
["Définition des besoins matériels","James","2016-05-17","2016-05-22",5,"TERMINÉ",null,"NON COMMENCÉ",6,{"$f":"I7/SUM(I4:I7)","v":0.42857142857142855}]
["Plannification des ressources finalisée","Anna","2016-05-23","2016-05-27",4,"EN RETARD"]
["Exposé aux investisseurs","Ken","2016-06-04","2016-06-05",1,"EN RETARD"]
["Recrutement du personnel","Sara","2016-06-01","2016-06-05",4,"EN COURS",null,"BUDGET"]
["Réalisation","James","2016-06-06","2016-06-27",21,"EN COURS"]
["Version alpha prête","Pete","2016-06-28","2016-06-29",1,"NON COMMENCÉ",null,"PROJETÉ","RÉEL","DIFFÉRENCE"]
["Tests alpha","Jason","2016-06-29","2016-07-15",16,"NON COMMENCÉ",null,1000000,880000,{"$f":"(H13-I13)","v":120000}]
["Version bêta prête","Pete","2016-07-16","2016-07-17",1,"NON COMMENCÉ"]
["Tests bêta","Jason","2016-07-17","2016-07-30",13,"NON COMMENCÉ"]
["Lancement","Pete","2016-08-01","2016-08-02",1,"NON COMMENCÉ"]
["Plannification à venir","Anna","2016-08-02","2016-08-04",2,"NON COMMENCÉ"]
[]
[]
["RISQUES ET ACTIONS EN COURS"]
["TÂCHES","RISQUES",null,null,"À RÉSOUDRE",null,"ACTIONS EN COURS"]
[null,"ÉLEVÉ","MOYEN","FAIBLE","PROBLÈMES","RÉVISIONS"]
["Démarrage du projet",1,0,4,2,0,4]
["Définition des objectifs",2,3,5,1,2,3]
["Définition des besoins du projet",3,4,3,2,1,2]
["Définition des besoins matériels",5,8,1,1,0,0]
["Plannification des ressources finalisée",8,6,4,0,3,1]
["Exposé aux investisseurs",5,0,0,2,0,2]
["Recrutement du personnel",6,4,0,1,2,3]
["Réalisation",7,3,3,0,1,4]
["Version alpha prête",0,2,4,1,3,2]
["Tests alpha",4,4,5,2,0,0]
["Version bêta prête",3,6,4,3,2,0]
["Tests bêta",2,3,6,0,1,1]
["Lancement",1,1,7,1,0,2]
["Plannification à venir",5,0,2,2,1,3]
[null,{"$f":"SUM(B23:B36)","v":52},44,48,18,16,27]