## Project Plan and Gantt
PROJECT PLAN TEMPLATE
Project Name | Product Release
Project Manager | Alex B.
Project Deliverable
Scope Statement:
Start Date | 2015-09-02
End Date | 2015-10-10
Overall Progress | 20%
Tasks | Responsible | Start | End | Days | Status
Set kick-off meeting | Alex B. | 2015-09-02 | 2015-09-03 | 1 | Complete
Agree on objectives | Frank C. | 2015-09-03 | 2015-09-07 | 4 | Complete
Detailed Reqs. | Jacob S. | 2015-09-07 | 2015-09-12 | 5 | Complete
Hardward Reqs. | Jacob S. | 2015-09-09 | 2015-09-11 | 2 | Overdue
Final Resource Plan | Jacob S. | 2015-09-11 | 2015-09-15 | 4 | In progress
Staffing | Alex B. | 2015-09-16 | 2015-09-17 | 1 | In progress
Techincal Reqs. | Frank C. | 2015-09-17 | 2015-09-21 | 4 | Not started
DB Development | Shari W. | 2015-09-22 | 2015-09-24 | 2 | Not started
API Development | Shari W. | 2015-09-23 | 2015-09-27 | 4 | Not started
UI Client | Alex B. | 2015-09-25 | 2015-09-29 | 4 | Not started
Testing | Kennedy K. | 2015-09-24 | 2015-10-02 | 8 | Not started
Dev. Complete | Jacob S. | 2015-10-02 | 2015-10-05 | 3 | Not started
Hardware Config. | Alex B. | 2015-10-05 | 2015-10-07 | 2 | Not started
System Testing | Kennedy K. | 2015-10-06 | 2015-10-09 | 3 | Not started
Launch |  | 2015-10-09 | 2015-10-10 | 1
CREATE YOUR PROJECT PLAN IN SMARTSHEET

## Stakeholder List
Stakeholder List
Name | Position | Role in project | Email address | Requirements | Expectations
John Smith | VP of Product | Final approval of milestones | john@123.com | Downtime of no longer than 20 minutes | QA to take less than 1 week, marketing to promote new features in newsletter

## Cost Baseline
Cost Baseline
Item/task | % Complete | Base Cost | Cost | Actual Cost | % Budget Spent
Extra devices for QA testing | 50% | 2800 | 3500 | 3600 | 15%

## Communication Plan
Communication Plan
Communication Type | Deliverable | Description | Delivery Method | Frequency | Owner | Audience
Presentation | 15-minute Powerpoint presentation | Presentation to marketing team about new features | In-person | One time | Alex B. | Marketing team
Meetings | Standup meetings | Check in about status | In-person | 2x a week | John S. | Project team

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.