## EX - Corrective Action Plan
Corrective Action Plan Template Example
Corrective Action Plan
Date | Deadline | Prepared By
2025-05-26 | 2025-06-16 | Director of IT
Problem Statement
A client reported unauthorized access to their account due to an unpatched security vulnerability in our login system.
Root Cause
The patch was missed during the Q1 deployment because of miscommunication between the Development and Security teams.
Action Step | Description | Status | Due Date | Person / Team Responsible | Desired Outcome
Patch vulnerability | Deploy the missed authentication patch to all affected environments | In Progress | 2025-05-29 | IT Security Team | Vulnerability eliminated across all systems
Conduct full security audit | Review all systems for additional outdated components or missed patches | Not Started | 2025-06-04 | DevOps & Security Audit Team | Ensure systemwide compliance with security protocols
Update deployment process documentation | Document procedures to ensure security updates are prioritized in sprint plans | Not Started | 2025-06-02 | Dev Team Lead | Reduced risk of skipped updates in future cycles
Results Assessment
The corrective actions resolved the vulnerability and improved coordination between teams. No further incidents have occurred since the patch was applied.
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Corrective Action Plan
Corrective Action Plan Template
Corrective Action Plan
Date | Deadline | Prepared By
Problem Statement
Root Cause
Action Step | Description | Status | Due Date | Person / Team Responsible | Desired Outcome
Not Started
In Progress
Complete
Results Assessment

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
STATUS
Not Started
In Progress
Complete

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.