## EXAMPLE Daily Activity Report
Daily Activity Report Template Example
Employee Name | Department / Team | Position / Role | Supervisor | Date
Alexandra Mattson | Field Operations / DC Fast Charging | Field Technician Lead | Marcus Liu | 10/02/20XX
Shift Start | Shift End | Total Hours (auto-calculates) | Location / Site / Job No. | Contact (Phone / Email
8:00 | 16:30 | 8.5 | Rose City Plaza DCFC Upgrade / Site RCP-07 / Job PC-OPS-078 | 503-555-0142 ¦ alexandra.mattson@positivecharge.io
Activity / Task | Start Time | End Time | Duration in minutes (auto-calculates) | Description / Notes | Outcome / Deliverable | Follow-Up Owner and Due Date
Pre-Shift Brief & Safety Check | 8:00 | 8:15 | 15 | Toolbox talk, PPE check, LOTO review, hazard scan. | Signed safety checklist uploaded to Ops folder. | A. Mattson – 10/03
Site Arrival & Setup | 8:15 | 8:35 | 20 | Cones/barriers placed; panel access verified; network cabinet powered. | Work zone established; equipment staged. | A. Mattson – 10/02
Cabinet Rewire & Torque Verification (Unit 2) | 8:35 | 11:05 | 150 | Retorqued busbars to spec; replaced CT sensor; verified ground. | Cabinet passed inspection; measurements logged. | J. Ortega to add torque values to asset record – 10/03
OCPP Provisioning & Firmware Update | 11:05 | 11:50 | 45 | Provisioned via Console; set 60-sec heartbeat; applied FW build 1.6J-P3. | Stable heartbeat; charger visible in dashboard. | R. Patel to schedule configuration audit – 10/06
0
0
End-of-Day Summary
Top Accomplishments (3 Bullets): Issues / Risks / Blockers: Plan For Tomorrow / Next Shift: Stakeholder Updates Sent (Who/How): Materials / Expenses / Mileage: Incidents (Time, Type, Brief Description, Reported To, Corrective Action): Notes / Lessons Learned:
Employee Name | Employee Signature | Date
Supervisor Name | Supervisor Signature | Date
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Daily Activity Report
Daily Activity Report Template
Employee Name | Department / Team | Position / Role | Supervisor | Date
Shift Start | Shift End | Total Hours (auto-calculates) | Location / Site / Job No. | Contact (Phone / Email
0
Activity / Task | Start Time | End Time | Duration in minutes (auto-calculates) | Description / Notes | Outcome / Deliverable | Follow-Up Owner and Due Date
0
0
0
0
0
0
0
End-of-Day Summary
Employee Name | Employee Signature | Date
Supervisor Name | Supervisor Signature | Date

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.