## EXAMPLE Issue Tracker Dashboard
Issue Tracker Dashboard Template Example
Campaign Name |  |  |  | Date | Project Status | % Complete
Platform Cleanup |  |  |  | 00/00/00 | In Progress | 58%
Issue Timeline
Dashboard Data
Issue Table
Issue ID | Project | Component | Status | Priority | Assignee | Raised By | Date Reported | Date Resolved | Resolution Time in days | Comments
ISS-001 | App Redesign | Login Module | Open | Critical | Leigh Gibbs | Romy Bailey | 2025-01-02 | 2025-01-08 | 7 | The login form is loading slowly.
ISS-002 | App Redesign | Notifications | In Progress | Low | Lori Garcia | Sasha Petrov | 2025-01-04 | 2025-01-11 | 8 | Fixed in the latest deploy
ISS-003 | Data Sync | API Connector | Closed | Medium | Makara McLean | Olivia Carter | 2025-01-07 | 2025-01-11 | 5 | Timeout error on sync start
ISS-004 | Web Portal | Dashboard Charts | Under Review | High | Marta Hicks | Petrus Nishimura | 2025-01-10 | 2025-01-15 | 6 | Review chart refresh logic
ISS-005 | CRM Integration | Email Service | Postponed | Critical | Mateus Tobin | Raghu Prakash | 2025-01-13 | 2025-01-20 | 8 | SMTP credentials updated
ISS-006 | CRM Integration | Lead Form | Closed | Low | Olivia Carter | Leigh Gibbs | 2025-01-16 | 2025-01-29 | 14 | Waiting on design approval
ISS-007 | Support Tool | Search | Closed | Medium | Petrus Nishimura | Sarah Goodwin | 2025-01-19 | 2025-02-01 | 14 | Results return incomplete
ISS-008 | Analytics Suite | Data Export | Under Review | High | Raghu Prakash | Marta Hicks | 2025-01-22 | 2025-02-09 | 19 | Bug in CSV format fixed
ISS-009 | Web Portal | User Settings | Open | Critical | Romy Bailey | Lori Garcia | 2025-01-25 | 2025-02-05 | 12 | Cannot update profile info
ISS-010 | Support Tool | Live Chat | Open | Low | Sarah Goodwin | Mateus Tobin | 2025-01-28 | 2025-02-06 | 10 | Messages not sending
ISS-011 | App Redesign | Onboarding Flow | Open | Medium | Sasha Petrov | Romy Bailey | 2025-01-31 | 2025-02-02 | 3 | Added missing tour steps
ISS-012 | Analytics Suite | Report Builder | Open | Critical | Leigh Gibbs | Raghu Prakash | 2025-02-03 | 2025-02-04 | 2 | Formatting errors in PDF
Status %
|  | STATUS | COUNT | %
|  | Open | 5 | 41.67%
|  | In Progress | 1 | 8.333%
|  | Closed | 3 | 25%
|  | Under Review | 2
|  | Postponed | 1 | 8.333%
|  | TOTAL | 12 | 83.33%
Priority %
|  | PRIORITY | COUNT | %
|  | Low | 3 | 37.5%
|  | Medium | 3 | 37.5%
|  | High | 2 | 25%
|  | Critical | 4 | 50%
|  | TOTAL | 8 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Issue Tracker Dashboard
Issue Tracker Dashboard Template
Campaign Name |  |  |  | Date | Project Status | % Complete
|  |  |  | 00/00/00 |  | 0% | Enter DASHBOARD DATA in the tables beginning at row 10. Dashboard graphics will automatically populate.
Issue Timeline
Dashboard Data
Issue Table
Issue ID | Project | Component | Status | Priority | Assignee | Raised By | Date Reported | Date Resolved | Resolution Time in days | Comments
[7 empty] | 2025-01-02 | 2025-01-08 | 7
0
0
0
0
0
0
0
0
0
0
0
Status %
|  | STATUS | COUNT | %
|  | Open | 0
|  | In Progress | 0
|  | Closed | 0
|  | Under Review | 0
|  | Postponed | 0
|  | TOTAL | 0 | 0%
Priority %
|  | PRIORITY | COUNT | %
|  | Low | 0
|  | Medium | 0
|  | High | 0
|  | Critical | 0
|  | TOTAL | 0 | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Open
No | Medium | In Progress
| High | Closed
| Critical | Under Review
Postponed

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.