## EXAMPLE Project Dashboard
Project Management Dashboard Template Example
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
PROJECT BETA |  |  |  | MM/DD/YY | ON TRACK | 45%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | RISK | PRIORITY | COMMENTS
Set Kick-Off Meeting | Alex B. | 2024-01-02 | 2024-01-08 | 6 | Complete | Low | Medium
Agree on objectives | Frank C. | 2024-01-04 | 2024-01-11 | 7 | In Progress | Medium | Low
Detail requests | Jacob S. | 2024-01-07 | 2024-01-11 | 4 | Overdue | High | High
Hardware requests | Jacob S. | 2024-01-10 | 2024-01-15 | 5 | In Progress | Low | Medium
Final resource plan | Jacob S. | 2024-01-13 | 2024-01-20 | 7 | Complete | Medium | Medium
Staffing | Alex B. | 2024-01-16 | 2024-01-29 | 13 | Complete | Low | Medium
Technical requests | Frank C. | 2024-01-19 | 2024-02-01 | 13 | Not Started | Low | Low
Training | Kennedy K. | 2024-01-22 | 2024-02-09 | 18 | In Progress | Medium | High
Testing | Jacob S. | 2024-01-25 | 2024-02-05 | 11 | Overdue | Medium | Low
Dev. Complete | Alex B. | 2024-01-28 | 2024-02-06 | 9 | Not Started | High | High
Hardware configuration | Kennedy K. | 2024-01-31 | 2024-02-02 | 2 | Overdue | High | High
System testing | Donald W. | 2024-02-03 | 2024-02-04 | 1 | Complete | High | High
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 80000
Not Started | 2 | 16.67% |  | ACTUAL | 50000
In Progress | 3 | 25%
Complete | 4 | 33.33%
Overdue | 3 | 25%
On Hold | 0 | 0%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 4 | 33.33% |  | Actions | 2
Medium | 4 | 33.33% |  | Change Requests | 4
Low | 4 | 33.33%
| 0 | 0%
TOTAL | 12 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Project Dashboard
Project Management Dashboard Template
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | MM/DD/YY | ON TRACK | 72% |  | Enter DASHBOARD DATA in the tables beginning at row 8. Dashboard graphics will automatically populate.
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | RISK | PRIORITY | COMMENTS
Candidate recruitment |  |  |  | 0 | Complete | High | Medium
Conduct disciplinary actions |  |  |  | 0 | Complete | High | Low
Design and update company policies |  |  |  | 0 | Complete | High | High
Maintain employee records |  |  |  | 0 | Complete | High | Medium
Conduct benefits analysis |  |  |  | 0 | Complete | High | Medium
Employee training and development |  |  |  | 0 | Complete | High | Medium
Conduct job analysis and role descriptions |  |  |  | 0 | Complete | High | Low
Monitor employee performance |  |  |  | 0 | Complete | High | High
Resolve employee internal conflicts |  |  |  | 0 | Complete | High | Low
Disburse rewards and incentives |  |  |  | 0 | Complete | High | High
Set standards for promotions |  |  |  | 0 | Complete | High | High
Investigate internal complaints |  |  |  | 0 | Complete | High | High
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 0
Not Started | 0 | 0% |  | ACTUAL | 0
In Progress | 0 | 0%
Complete | 12 | 100%
Overdue | 0 | 0%
On Hold | 0 | 0%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 12 | 100% |  | Actions | 0
Medium | 0 | 0% |  | Change Requests | 0
Low | 0 | 0%
| 0 | 0%
TOTAL | 12 | 100%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown keys - DO NOT DELETE
DROP DOWN KEYS - DO NOT DELETE
STATUS | PRIORITY / RISK
Not Started | High
In Progress | Medium
Complete | Low
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.