## Project Planning Gantt
Project Planning Gantt Template with Risk and Resources
Project Title |  |  | Start Date
|  |  | 2024-01-02 |  |  | Project Duration
Project Manager |  |  | End Date |  |  | in days
|  |  | 2024-03-26 |  |  | 85
WBS NO. | Task Name | Status | Assigned To | Start Date | End Date | Duration in days | Resource Type | Risk Level | Milestone | Comments
1 | Project Conception and Initiation | Complete |  | 2024-01-02 | 2024-02-09 | 39
1.1 | – Project Charter | Complete | Diana Kennedy | 2024-01-02 | 2024-01-11 | 10 | Internal | Low | Yes | Charter approved by the executive team; ready for archive
1.1.1 | –– Project Charter Revisions | In Progress | Diana Kennedy | 2024-01-07 | 2024-01-11 | 5 | Internal | Medium | No | Final edits addressed; updated version stored
1.2 | – Research | On Hold | Fiorella Fitzgerald | 2024-01-10 | 2024-02-23 | 45 | Consultant | High | Yes | Vendor comparison complete; sources cited
1.3 | – Projections | Not Started | Jonathon Wong | 2024-01-10 | 2024-01-20 | 11 | Finance | Low | Yes | Financial projections reviewed; assumptions updated
1.4 | – Stakeholders | Complete | Jamal King | 2024-01-16 | 2024-01-29 | 14 | Internal | Low | No | Documented stakeholder engagement; feedback was minimal
1.5 | – Guidelines | Complete | Jamal King | 2024-01-19 | 2024-02-01 | 14 | Internal | Low | Yes | Branding guidelines drafted; pending design review
1.6 | – Project Initiation | Complete | Diana Kennedy | 2024-01-22 | 2024-02-09 | 19 | Internal | Low | Yes | The initiation checklist is underway; final sign-off is needed
2 | Project Definition and Planning |  |  | 2024-01-28 | 2024-02-14 | 18
2.1 | – Scope & Goal Setting |  | Jason Desjardins | 2024-01-28 | 2024-02-06 | 10 | Internal |  |  | Goals and success criteria aligned with leadership OKRs
2.2 | – Budget |  | Everett Crosse | 2024-01-31 | 2024-02-02 | 3 | Finance |  |  | Preliminary budget created; pending approval from finance lead
2.3 | – Communication Plan |  | Jonathon Wong | 2024-02-04 | 2024-02-12 | 9 | Internal |  |  | Comms channels selected; team contact matrix finalized
2.4 | – Risk Management |  | Jason Desjardins | 2024-02-06 | 2024-02-14 | 9 | Consultant |  |  | Risk log initiated; first review with PM scheduled
3 | Project Launch and Execution |  |  | 2024-02-18 | 2024-03-26 | 38
3.1 | – Status & Tracking |  | Diana Kennedy | 2024-02-18 | 2024-02-20 | 3 | Internal |  |  | Weekly status check-ins established; updates begin Monday
3.2 | – KPIs |  | Fiorella Fitzgerald | 2024-02-18 | 2024-02-23 | 6 | Internal |  |  | KPI framework aligned with phase milestones
3.2.1 | –– Monitoring |  | Fiorella Fitzgerald | 2024-02-18 | 2024-02-26 | 9 | Internal |  |  | Dashboard setup in progress; test metrics entered
3.2.2 | –– Forecasts |  | Jason Desjardins | 2024-02-21 | 2024-02-23 | 3 | Data Analyst |  |  | Forecasting model built; awaiting data from reporting team
3.3 | – Project Updates |  | Everett Crosse | 2024-02-22 | 2024-02-23 | 2 | Internal |  |  | Update cycle defined; shared across teams
3.3.1 | –– Chart Updates |  | Everett Crosse | 2024-02-25 | 2024-03-26 | 31 | Internal |  |  | Chart design finalized; format standardized for reuse
4 | Project Performance / Monitoring |  |  | 2024-02-25 | 2024-03-26 | 31
4.1 | – Project Objectives |  | Diana Kennedy | 2024-02-25 | 2024-02-28 | 4 | Internal |  |  | Scope and objectives revalidated; KPIs linked
4.2 | – Quality Deliverables |  | Jonathon Wong | 2024-02-26 | 2024-03-03 | 7 | QA Team |  |  | QA backlog updated; key bugs prioritized for Sprint 3
4.3 | – Effort & Cost Tracking |  | Everett Crosse | 2024-02-25 | 2024-03-06 | 11 | Finance |  |  | Cost reporting module connected to the main dashboard
4.4 | – Project Performance |  | Jonathon Wong | 2024-03-03 | 2024-03-26 | 24 | Internal |  |  | Performance thresholds under review; metrics validated
CLICK HERE TO CREATE IN SMARTSHEET

## Dropdown Key - Do Not Delete
Dropdown Keys - Do Not Delete
Status | Risk Level | Milestone
Not Started | Low | Yes
In Progress | Medium | No
Complete | High
On Hold

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.