## Risk Response Matrix
Risk Response Matrix Template
|  | 1 | 2 | 3 | 4 | 5
|  | RETAIN | RETAIN | RETAIN | TRANSFER | TRANSFER
| 1 | 1 | 2 | 3 | 4 | 5
|  | RETAIN | TRANSFER | TRANSFER | MITIGATE | MITIGATE
| 2 | 2 | 4 | 6 | 8 | 10
|  | RETAIN | TRANSFER | MITIGATE | MITIGATE | AVOID
| 3 | 3 | 6 | 9 | 12 | 15
|  | TRANSFER | MITIGATE | MITIGATE | MITIGATE | AVOID
| 4 | 4 | 8 | 12 | 16 | 20
|  | TRANSFER | MITIGATE | AVOID | AVOID | AVOID
| 5 | 5 | 10 | 15 | 20 | 25
CLICK HERE TO CREATE IN SMARTSHEET
IMPACT
PROBABILITY

## Risk Register
Risk Register
Risk ID | Title | Description | Category | Probability | Impact | Risk Score | Response Type | Owner | Planned Response | Status | Target Date
|  |  |  | 1 | 2 | 2 | Retain |  |  | Open
|  |  |  | 2 | 3 | 6 | Transfer |  |  | In Progress
|  |  |  | 3 | 4 | 12 | Mitigate |  |  | Mitigated
|  |  |  | 4 | 5 | 20 | Avoid |  |  | Closed
|  |  |  | 5 | 1 | 5 | Transfer
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
[6 empty] | 0 | Retain
How to use this Matrix
1. Identify the risk, clearly describe it, and assign it an ID.
2. Rate how likely the risk is to occur.
1 - 2 = Unlikely
3 - 4 = Possible
5 = Almost Certain
3. Score the Impact.
1 - 2 = Minimal Impact
3 - 4 = Moderate Impact
5 = Critical Impact
4. Calculate the risk score. Multiply probability by impact to determine overall risk severity.
5. Determine the response strategy.
Avoid: Eliminate the risk.
Transfer: Shift the risk to a third party.
Mitigate: Reduce the likelihood or impact.
Retain: Accept and monitor the risk.
6. Plan and assign actions
7. Monitor and review

## - Drop Down Lists -
Drop Down Lists Do Not Delete
Status
Open
In Progress
Mitigated
Closed

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.