## Example Issue Tracking
Simple Issue Tracking Template Example
Company |  | Weller Valley Inc.
Department |  | Development
Project Name |  | Project Alpha
Project Manager |  | Aviv Perez
Issue Number | Status | Description | Category | Priority | Assignee | Raised By | Date Reported | Date Resolved | Resolution Time | Comments
ISS-001 | Open | dropdown failure | Bug | High | Alexandra Mattson | Jamal King | 2032-01-04
ISS-002 | In Progress | error on login | Bug | Medium | Brian Gorman | Fiorella Fitzgerald | 2032-01-05
ISS-003 | Closed | label missing | Task | Low | Aviv Perez | Brooklyn Jansen | 2032-01-07 | 2032-01-08 | 1
ISS-004 | Closed | wrong link footer | Bug | Medium | Diana Kennedy | Hilda Wilson | 2032-01-08 | 2032-01-09 | 1
ISS-005 | Open | mobile crash | Bug | High | Hazel Christensen | Everett Crosse | 2032-01-09
ISS-006 | In Progress | title misaligned | Task | Low | Everett Crosse | Guadalupe Garcia | 2032-01-10
ISS-007 | Closed | Update profile bug | Bug | Medium | Hilda Wilson | Jason Desjardins | 2032-01-11 | 2032-01-13 | 2
ISS-008 | Closed | color mismatch | Task | Low | Guadalupe Garcia | Carmen Robertson | 2032-01-13 | 2032-01-14 | 1
ISS-009 | Open | 500 error dashboard | Bug | Critical | Brooklyn Jansen | Alexandra Mattson | 2032-01-15
ISS-010 | In Progress | FAQ load failure | Bug | High | Henry McNeal | Devon Gomez | 2032-01-15
ISS-011 | Closed | button overlap | Task | Low | Diana Kennedy | Hilda Wilson | 2032-01-16 | 2032-01-17 | 1
ISS-012 | Closed | typo on welcome | Task | Low | Fiorella Fitzgerald | Aviv Perez | 2032-01-17 | 2032-01-18 | 1
ISS-013 | Closed | missing validation | Feature | High | Jamal King | Alexandra Mattson | 2032-01-18 | 2032-01-22 | 4
ISS-014 | In Progress | table overflow | Task | Medium | Henry McNeal | Hazel Christensen | 2032-01-19
ISS-015 | Open | export not working | Bug | High | Jason Desjardins | Diana Kennedy | 2032-01-19
ISS-016 | Closed | feature misfiring | Feature | Medium | Hilda Wilson | Carmen Robertson | 2032-01-20 | 2032-01-22 | 2
ISS-017 | Closed | alert not closing | Bug | Medium | Carmen Robertson | Alexandra Mattson | 2032-01-21
ISS-018 | In Progress | icon flicker | Task | Low | Devon Gomez | Henry McNeal | 2032-01-22 | 2032-01-23 | 1
ISS-019 | Closed | dark mode overlap | Feature | Medium | Carmen Robertson | Brian Gorman | 2032-01-23 | 2032-01-25 | 2
ISS-020 | Open | newsletter bug | Bug | High | Fiorella Fitzgerald | Jamal King | 2032-01-24
ISS-021 | In Progress | delay on submit | Bug | Medium | Alexandra Mattson | Diana Kennedy | 2032-01-25
ISS-022 | Closed | dropdown resets | Bug | High | Henry McNeal | Brooklyn Jansen | 2032-01-26 | 2032-01-28 | 2
ISS-023 | Open | section not loading | Bug | High | Jamal King | Guadalupe Garcia | 2032-01-28
ISS-024 | In Progress | field labels clipped | Task | Low | Jason Desjardins | Hazel Christensen | 2032-01-29
ISS-025 | Open | search fails | Bug | Critical | Brian Gorman | Everett Crosse | 2032-01-30
CLICK HERE TO CREATE IN SMARTSHEET

## Blank Issue Tracking
Simple Issue Tracking Template
Company
Department
Project Name
Project Manager
Issue Number | Status | Description | Category | Priority | Assignee | Raised By | Date Reported | Date Resolved | Resolution Time | Comments
| Open |  | Bug | Medium

## Key - Do Not Delete
Key - Do Not Delete
Status | Category | Priority
Open | Bug | Low
In Progress | Feature | Medium
Closed | Task | High
| Request | Critical

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.