## Strategic Plan
Software Upgrade Project Plan Template
Strategic Plan
Executive Summary
Project Objectives
Scope Statement
Expected Business Impact
Pre-Upgrade Analysis
Requirements
Functional
Technical
Hardware/Software Compatibility Check | Conduct a hardware and software compatibility check for all systems, servers, and user workstations that will be affected and confirm their compatibility with the new version.
Budget
Category | Estimated Cost | Actual Cost | Notes | Software Licensing | 3rd-Party Consultants | Staff Overtime | Training | Total
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
| 0 | 0 |  | 0 | 0 | 0 | 0 | 0
Resource Allocation
Role | Name | Responsibilities | Project Sponsor | Project Manager | Technical Lead | QA/Testing Lead | Training Lead
Risk Management
Risk ID | Risk Description |  | Likelihood (H/M/L) | Impact (H/M/L) | Mitigation Strategy |  | Owner
Stakeholder and Communication Plan
Stakeholder Group |  | Key Message |  |  | Channel | Frequency | Owner
Contingency and Testing Plan
A. Test Plan ¦ Step-by-step process for testing in a non-production or sandbox environment.
1. Sandbox Environment Setup | Clone production data to sandbox.
2. Technical Tests | Install upgrade in sandbox. Verify integrations, APIs, and data integrity.
3. User Acceptance Testing (UAT) | Have power-users test key workflows.
4. Sign-Off | Receive formal approval from QA Lead and Business Owner.
B. Rollback Plan ¦ Step-by-step process for reverting the upgrade if it fails. This plan is a "panic button" and must be clearly defined.
Trigger: | Rollback will be triggered if: (a) ..., OR (b) …
Step 1 | Project Manager declares a "NO-GO" and authorizes the rollback.
Step 2 | Technical Lead begins restore from pre-upgrade backup.
Step 3
Step 4
Contingency and Testing Plan
User Training ¦ Outline the plan to train users on the new software version. Include the audience, format, and date.
Helpdesk Support ¦ Describe the support plan for the days immediately following launch.
Performance Monitoring ¦ How will you measure success?
CLICK HERE TO CREATE IN SMARTSHEET

## Project Timeline and Tasks
Project Timeline and Tasks
Project Title |  |  | Start Date
|  |  | 2025-01-02 |  |  | Project Duration
Project Manager |  |  | End Date |  |  | (in days)
|  |  | 2025-06-01 |  |  | 151
Phase | Task name | Status | Owner | Start Date | End Date | Duration (in days) | Comments | Status
1 | Analysis and Scoping |  |  | 2025-01-02 | 2025-02-09 | 39 |  | Not Started
1.1 | – Initial Spec and Document Review | Complete |  | 2025-01-02 | 2025-01-11 | 10 |  | In Progress
1.1.1 | – Form Project Team and Define Roles | Complete |  | 2025-01-07 | 2025-01-11 | 5 |  | Complete
1.2 | – Hardware Assessment | Complete |  | 2025-01-10 | 2025-02-23 | 45 |  | On Hold
1.3 | – System Compatibility Check | Complete |  | 2025-01-10 | 2025-01-20 | 11
1.4 | – Finalize Budget and Resource Plan | Complete |  | 2025-01-16 | 2025-01-29 | 14
1.5 | – Phase 1 Sign-Off | Complete |  | 2025-01-19 | 2025-02-01 | 14
2 | Timeline and Resource Planning |  |  | 2025-01-28 | 2025-02-14 | 18
2.1 | – Task Time Estimation | On Hold |  | 2025-01-28 | 2025-02-06 | 10
2.2 | – Finalize Resource Allocation | In Progress |  | 2025-01-31 | 2025-02-02 | 3
2.3 | – Develop Communication Plan | In Progress |  | 2025-02-04 | 2025-02-12 | 9
2.4 | – Develop Risk Management Plan | Complete |  | 2025-02-06 | 2025-02-14 | 9
2.5 | – Develop Contingency Planning | In Progress |  | 2025-02-08 | 2025-02-16 | 9
3 | Pre-Implementation (Testing and Backup) |  |  | 2025-02-18 | 2025-03-26 | 37
3.1 | – Data Backup Strategy and Verification | In Progress |  | 2025-02-18 | 2025-02-20 | 3
3.2 | – Create Test/Sandbox Environment | In Progress |  | 2025-02-18 | 2025-02-23 | 6
3.3 | – User Notification (Initial) | In Progress |  | 2025-02-18 | 2025-02-26 | 9
3.4 | – Sandbox and UAT Testing | Not Started |  | 2025-02-21 | 2025-02-23 | 3
3.5 | – Resolve Bugs Found in Testing | Not Started |  | 2025-02-22 | 2025-02-23 | 2
3.6 | – Final Rollback Plan Finalization | In Progress |  | 2025-02-25 | 2025-03-26 | 30
3.7 | – Phase 3 Go/No-Go Meeting | Not Started |  | 2025-02-20 | 2025-02-20 | 1
4 | Go-Live Execution |  |  | 2025-02-25 | 2025-03-26 | 30
4.1 | – Send Final Downtime Notification | Not Started |  | 2025-02-25 | 2025-02-28 | 4
4.2 | – Perform Final Data Backup | Not Started |  | 2025-03-01 | 2025-03-05 | 5
4.3 | – Downtime Commencement (System Offline) | Not Started |  | 2025-03-05 | 2025-03-08 | 4
4.4 | – Upgrade Installation | Not Started |  | 2025-03-09 | 2025-03-15 | 7
4.5 | – Initial System Tests (By Tech Team) | Not Started |  | 2025-03-16 | 2025-03-17 | 2
4.6 | – System Restart (Go-Live) | Not Started |  | 2025-03-20 | 2025-03-20 | 1
4.7 | – Send "System Is Live" Communication | Not Started |  | 2025-03-20 | 2025-03-26 | 7
5 | Post-Launch Review |  |  | 2025-03-27 | 2025-04-30 | 35
5.1 | – System Performance Monitoring | Not Started |  | 2025-03-27 | 2025-04-30 | 35
5.2 | – Helpdesk Support | Not Started |  | 2025-03-26 | 2025-05-01 | 37
5.3 | – Resolve Priority 1 Bugs | Not Started |  | 2025-04-30 | 2025-05-01 | 2
5.4 | – User Satisfaction Survey | Not Started |  | 2025-05-01 | 2025-05-01 | 1
5.5 | – Lesson Learned and Project Closure | Not Started |  | 2025-05-01 | 2025-05-01 | 1

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.