## Client Onboarding
CLIENT ONBOARDING TEMPLATE
AT RISK SUMMARY |  | STATUS SUMMARY
AT RISK | 7 | Not Started | 20
|  | In Progress | 1
|  | Complete | 2
|  | On Hold | 1
|  | Overdue | 1
|  | Needs Review | 1
|  | Canceled | 1
AT RISK | TASK NAME | STATUS | CLIENT OWNER | INTERNAL OWNER | START DATE | END DATE | DURATION | % COMPLETE | PREDECESSORS
- | Onboarding Plan |  |  |  | 2025-06-26 | 2025-09-03 | 50 | 11.48% |  | AT RISK | STATUS
- | Initiation |  |  |  | 2025-06-26 | 2025-06-28 | 2 | 42% |  | X | Not Started
X | Statement of Work | Complete | TBD | Example Name | 2025-06-26 | 2025-06-26 | 1 | 100% |  |  | In Progress
X | Establish Onboarding Team | In Progress | TBD | Example Name | 2025-06-27 | 2025-06-27 | 1 | 50% | 10 |  | Complete
| Welcome Email | On Hold | TBD | Example Name | 2025-06-27 | 2025-06-27 | 1 | 20% |  |  | On Hold
| Prepare Welcome Email | Needs Review | TBD | Example Name | 2025-06-27 | 2025-06-27 | 1 | 40% | 10 |  | Overdue
| Send Welcome Email | Not Started | TBD | Example Name | 2025-06-27 | 2025-06-27 | 1 | 0% | 13 |  | Needs Review
- | Plan |  |  |  | 2025-07-03 | 2025-07-12 | 7 | 16.67% |  |  | Canceled
| Kickoff Call | Canceled | TBD | TBD | 2025-07-03 | 2025-07-05 | 2 | 0%
X | Conduct Kickoff Call | Complete | TBD | TBD | 2025-07-03 | 2025-07-03 | 1 | 100% | 14FS +2d
X | Kickoff Call Follow-Up | Overdue | TBD | TBD | 2025-07-07 | 2025-07-07 | 1 | 0% | 17FS +1d
X | Onboarding Milestones | Not Started | TBD | TBD | 2025-07-07 | 2025-07-12 | 5 | 0%
X | Update Onboarding Milestones | Not Started | TBD | TBD | 2025-07-07 | 2025-07-10 | 4 | 0% | 18
X | Flag Onboarding Milestones | Not Started | TBD | TBD | 2025-07-11 | 2025-07-11 | 1 | 0% | 20
- | Pre-Launch |  |  |  | 2025-07-13 | 2025-08-23 | 30 | 0%
| Product and Process Framework | Not Started | TBD | TBD | 2025-07-13 | 2025-07-19 | 5 | 0%
| Design and Draft Framework | Not Started | TBD | TBD | 2025-07-13 | 2025-07-17 | 4 | 0% | 21
| Review with Client | Not Started | TBD | TBD | 2025-07-18 | 2025-07-18 | 1 | 0% | 24
| Update and Finalize Framework | Not Started | TBD | TBD | 2025-07-21 | 2025-07-21 | 1 | 0% | 25
| Proof Of Concept | Not Started | TBD | TBD | 2025-07-21 | 2025-08-16 | 20 | 0%
| Initial Proof of Concept | Not Started | TBD | TBD | 2025-07-21 | 2025-08-09 | 15 | 0% | 26
| Review and Update with Client | Not Started | TBD | TBD | 2025-08-11 | 2025-08-16 | 5 | 0% | 28
| Document | Not Started | TBD | TBD | 2025-08-17 | 2025-08-22 | 5 | 0%
| Document the Solution | Not Started | TBD | TBD | 2025-08-17 | 2025-08-22 | 5 | 0% | 29
| Send Documentation to Client | Not Started | TBD | TBD | 2025-08-22 | 2025-08-22 | 1 | 0% | 31
| Launch |  |  |  | 2025-08-24 | 2025-09-03 | 8 | 0%
| Data Set-Up | Not Started | TBD | TBD | 2025-08-25 | 2025-08-27 | 3 | 0%
| Establish Process for Client | Not Started | TBD | TBD | 2025-08-25 | 2025-08-25 | 1 | 0% | 32
| Conduct Data Transfer | Not Started | TBD | TBD | 2025-08-27 | 2025-08-27 | 1 | 0% | 35
| Implementation | Not Started | TBD | TBD | 2025-08-27 | 2025-09-03 | 6 | 0%
| Provide Completed Solution | Not Started | TBD | TBD | 2025-08-27 | 2025-08-27 | 1 | 0% | 36
| Launch with Client | Not Started | TBD | TBD | 2025-08-28 | 2025-09-03 | 5 | 0% | 38
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
DURATION = NETWORKDAYS([START DATE],[END DATE])

## BLANK - Client Onboarding
CLIENT ONBOARDING PLAN
AT RISK SUMMARY |  | STATUS SUMMARY
AT RISK | 0 | Not Started | 0
|  | In Progress | 0
|  | Complete | 0
|  | On Hold | 0
|  | Overdue | 0
|  | Needs Review | 0
|  | Canceled | 0
AT RISK | TASK NAME | STATUS | CLIENT OWNER | INTERNAL OWNER | START DATE | END DATE | DURATION | % COMPLETE | PREDECESSORS
- | Onboarding Plan | [5 empty] | 0 | 0% |  | AT RISK | STATUS
- | Initiation | [5 empty] | 0 | 0% |  | X | Not Started
| Statement of Work | [5 empty] | 0 | 0% |  |  | In Progress
| Establish Onboarding Team | [5 empty] | 0 | 0% |  |  | Complete
| Welcome Email | [5 empty] | 0 | 0% |  |  | On Hold
| Prepare Welcome Email | [5 empty] | 0 | 0% |  |  | Overdue
| Send Welcome Email | [5 empty] | 0 | 0% |  |  | Needs Review
| Plan | [5 empty] | 0 | 0% |  |  | Canceled
| Kickoff Call | [5 empty] | 0 | 0%
| Conduct Kickoff Call | [5 empty] | 0 | 0%
| Kickoff Call Follow-up | [5 empty] | 0 | 0%
| Onboarding Milestones | [5 empty] | 0 | 0%
| Update Onboarding Milestones | [5 empty] | 0 | 0%
| Flag Onboarding Milestones | [5 empty] | 0 | 0%
- | Pre-Launch | [5 empty] | 0 | 0%
| Product and Process Framework | [5 empty] | 0 | 0%
| Design and Draft Framework | [5 empty] | 0 | 0%
| Review with Client | [5 empty] | 0 | 0%
| Update and Finalize Framework | [5 empty] | 0 | 0%
| Proof Of Concept | [5 empty] | 0 | 0%
| Initial Proof of Concept | [5 empty] | 0 | 0%
| Review and Update with Client | [5 empty] | 0 | 0%
| Document | [5 empty] | 0 | 0%
| Document the Solution | [5 empty] | 0 | 0%
| Send Documentation to Client | [5 empty] | 0 | 0%
| Launch | [5 empty] | 0 | 0%
| Data Set-Up | [5 empty] | 0 | 0%
| Establish Process for Client | [5 empty] | 0 | 0%
| Conduct Data Transfer | [5 empty] | 0 | 0%
| Implementation | [5 empty] | 0 | 0%
| Provide Completed Solution | [5 empty] | 0 | 0%
| Launch with Client | [5 empty] | 0 | 0%
Formulas:
DURATION = NETWORKDAYS([START DATE],[END DATE])

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.