## Construction Est Worksheet
CONSTRUCTION ESTIMATING WORKSHEET – HOUSE
JOB TITLE |  |  | PROJECT MGR |  |  | PROJECTED START DATE
LOCATION | [5 empty] | PROJECTED END DATE
| PROJECTED TOTAL | ACTUAL TOTAL | DIFFERENCE
| 0 | 0 | 0
CATEGORY & ITEMS | PROJECTED SUBTOTAL | ACTUAL SUBTOTAL | DIFFERENCE | PARTY RESPONSIBLE Vendor, Contractor, etc. | STATUS | PCT OF TASK COMPLETE | COMMENTS | STATUS KEY
PLANNING | 0 | 0 | 0 |  |  | 0% |  | NOT STARTED
Admin Fees |  |  | 0 |  |  | 0% |  | IN PROGRESS
Engineering |  |  | 0 |  |  | 0% |  | COMPLETE
Financing Costs |  |  | 0 |  |  | 0% |  | ON HOLD
Legal |  |  | 0 |  |  | 0%
Permit - Building |  |  | 0 |  |  | 0%
Permit - Environmental |  |  | 0 |  |  | 0%
Permit - Zoning |  |  | 0 |  |  | 0%
Plans + Specs |  |  | 0 |  |  | 0%
Review |  |  | 0 |  |  | 0%
Survey |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
SITE PREP | 0 | 0 | 0 |  |  | 0%
Dumpster / Waste Removal |  |  | 0 |  |  | 0%
Equipment Rental |  |  | 0 |  |  | 0%
Lot Clearing |  |  | 0 |  |  | 0%
Portable Restroom Facilities |  |  | 0 |  |  | 0%
Remodel - Demo |  |  | 0 |  |  | 0%
Remodel - Dust Control |  |  | 0 |  |  | 0%
Remodel - Jacking + Shoring |  |  | 0 |  |  | 0%
Remodel - Surface Protection |  |  | 0 |  |  | 0%
Scaffolding Rental |  |  | 0 |  |  | 0%
Site Access |  |  | 0 |  |  | 0%
Site Security |  |  | 0 |  |  | 0%
Site Storage |  |  | 0 |  |  | 0%
Temporary Heat |  |  | 0 |  |  | 0%
Temporary Power |  |  | 0 |  |  | 0%
Tool Rental |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
EARTHWORK / EXCAVATION | 0 | 0 | 0 |  |  | 0%
Backfill |  |  | 0 |  |  | 0%
Blasting |  |  | 0 |  |  | 0%
Compaction |  |  | 0 |  |  | 0%
Culverts |  |  | 0 |  |  | 0%
Curtain Drains |  |  | 0 |  |  | 0%
Cut + Fill |  |  | 0 |  |  | 0%
Dirt + Stone Removal |  |  | 0 |  |  | 0%
Finish Grading |  |  | 0 |  |  | 0%
Foundation - Excavation |  |  | 0 |  |  | 0%
Foundation - Footing Drains |  |  | 0 |  |  | 0%
Ponds |  |  | 0 |  |  | 0%
Retaining Walls |  |  | 0 |  |  | 0%
Rough Grading |  |  | 0 |  |  | 0%
Seeding / Sodding |  |  | 0 |  |  | 0%
Site Drainage - Additional |  |  | 0 |  |  | 0%
Swales |  |  | 0 |  |  | 0%
Top Soil |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
UTILITIES | 0 | 0 | 0 |  |  | 0%
Electrical - Connection |  |  | 0 |  |  | 0%
Electrical - Install |  |  | 0 |  |  | 0%
Electrical - Permit |  |  | 0 |  |  | 0%
Gas - Connection |  |  | 0 |  |  | 0%
Gas - Hookup |  |  | 0 |  |  | 0%
Gas - Permit |  |  | 0 |  |  | 0%
Oil Tank Install |  |  | 0 |  |  | 0%
Sewer - Tap Fees & Hookup |  |  | 0 |  |  | 0%
Telecom - Hookup |  |  | 0 |  |  | 0%
Telecom - Install |  |  | 0 |  |  | 0%
Water - Tap Fees & Hookup |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
WATER + SEWER | 0 | 0 | 0 |  |  | 0%
High Water Table Dewatering |  |  | 0 |  |  | 0%
Perc Test |  |  | 0 |  |  | 0%
Plumbing to House |  |  | 0 |  |  | 0%
Pressure Tank |  |  | 0 |  |  | 0%
Pump |  |  | 0 |  |  | 0%
Septic - Design |  |  | 0 |  |  | 0%
Septic - Fees |  |  | 0 |  |  | 0%
Septic - Inspection |  |  | 0 |  |  | 0%
Septic - Permits |  |  | 0 |  |  | 0%
Septic - Tie to House |  |  | 0 |  |  | 0%
Soil Test |  |  | 0 |  |  | 0%
Trenching |  |  | 0 |  |  | 0%
Well |  |  | 0 |  |  | 0%
Well - Fees |  |  | 0 |  |  | 0%
Well - Permits |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
FOUNDATION | 0 | 0 | 0 |  |  | 0%
Anchor Bolts |  |  | 0 |  |  | 0%
Bulkheads |  |  | 0 |  |  | 0%
Crawlspace Vapor Barrier |  |  | 0 |  |  | 0%
Crawlspace Vents |  |  | 0 |  |  | 0%
Dam Proofing |  |  | 0 |  |  | 0%
Exterior Foundation Insulation |  |  | 0 |  |  | 0%
Exterior Insulation Coating |  |  | 0 |  |  | 0%
Footings |  |  | 0 |  |  | 0%
Foundation - Drain Board |  |  | 0 |  |  | 0%
Foundation - Walls |  |  | 0 |  |  | 0%
Foundation - Windows |  |  | 0 |  |  | 0%
Grade Beams |  |  | 0 |  |  | 0%
Hold Downs |  |  | 0 |  |  | 0%
Pads |  |  | 0 |  |  | 0%
Piers |  |  | 0 |  |  | 0%
Slab - Basement |  |  | 0 |  |  | 0%
Slab - Foundation |  |  | 0 |  |  | 0%
Slab - Garage |  |  | 0 |  |  | 0%
Slab Insulation |  |  | 0 |  |  | 0%
Steel Reinforcing |  |  | 0 |  |  | 0%
Stem Walls |  |  | 0 |  |  | 0%
Sub-Slab Vapor Barrier |  |  | 0 |  |  | 0%
Sump Pump |  |  | 0 |  |  | 0%
Waterproofing |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
ROUGH FRAMING | 0 | 0 | 0 |  |  | 0%
Exterior Walls |  |  | 0 |  |  | 0%
Fasteners / Nails / Screws |  |  | 0 |  |  | 0%
Floor Framing |  |  | 0 |  |  | 0%
Interior Walls |  |  | 0 |  |  | 0%
Lally Columns |  |  | 0 |  |  | 0%
Plaster / Drywall Prep |  |  | 0 |  |  | 0%
Roof Framing / Trusses |  |  | 0 |  |  | 0%
Rough Stairs |  |  | 0 |  |  | 0%
Sheathing |  |  | 0 |  |  | 0%
Sill + Seal |  |  | 0 |  |  | 0%
Steel / Wood Carrying Beam |  |  | 0 |  |  | 0%
Steel Framing Connectors |  |  | 0 |  |  | 0%
Sub-Fascia |  |  | 0 |  |  | 0%
Subflooring |  |  | 0 |  |  | 0%
Labor Costs |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
WINDOWS + DOORS (Exterior) | 0 | 0 | 0 |  |  | 0%
Exterior Door - Frames + Sills |  |  | 0 |  |  | 0%
Exterior Door - Hardware |  |  | 0 |  |  | 0%
Exterior Door - Prehung |  |  | 0 |  |  | 0%
Exterior Door - Slabs |  |  | 0 |  |  | 0%
Garage Doors |  |  | 0 |  |  | 0%
Membrane + Flashing |  |  | 0 |  |  | 0%
Sidelights |  |  | 0 |  |  | 0%
Sliding / Hinged Doors |  |  | 0 |  |  | 0%
Transoms |  |  | 0 |  |  | 0%
Windows |  |  | 0 |  |  | 0%
Labor Costs |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
FINISH - EXTERIOR | 0 | 0 | 0 |  |  | 0%
Foam Sheathing |  |  | 0 |  |  | 0%
Weather Barrier |  |  | 0 |  |  | 0%
Membrane + Flashing |  |  | 0 |  |  | 0%
Siding |  |  | 0 |  |  | 0%
Veneer |  |  | 0 |  |  | 0%
Stucco |  |  | 0 |  |  | 0%
Fascia |  |  | 0 |  |  | 0%
Soffit |  |  | 0 |  |  | 0%
Frieze |  |  | 0 |  |  | 0%
Corner Boards |  |  | 0 |  |  | 0%
Water Table |  |  | 0 |  |  | 0%
Soffit / Gable Vents |  |  | 0 |  |  | 0%
Trim - Windows |  |  | 0 |  |  | 0%
Trim - Doors |  |  | 0 |  |  | 0%
Trim - Finishing |  |  | 0 |  |  | 0%
Stairs |  |  | 0 |  |  | 0%
Landing |  |  | 0 |  |  | 0%
Paint |  |  | 0 |  |  | 0%
Stain |  |  | 0 |  |  | 0%
Caulk |  |  | 0 |  |  | 0%
Labor Costs |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
ROOFING | 0 | 0 | 0 |  |  | 0%
Drip Edge |  |  | 0 |  |  | 0%
Gutters + Downspouts |  |  | 0 |  |  | 0%
Installation / Labor |  |  | 0 |  |  | 0%
Membrane + Flashing |  |  | 0 |  |  | 0%
Ridge and Roof Vents |  |  | 0 |  |  | 0%
Skylights |  |  | 0 |  |  | 0%
Underlayment |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
MASONRY / PAVING | 0 | 0 | 0 |  |  | 0%
Driveway |  |  | 0 |  |  | 0%
Walkways |  |  | 0 |  |  | 0%
Chimneys |  |  | 0 |  |  | 0%
Stairs - Exterior |  |  | 0 |  |  | 0%
Patios |  |  | 0 |  |  | 0%
Fireplaces + Hearths |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
PORCHES + DECKS | 0 | 0 | 0 |  |  | 0%
Porch - Open |  |  | 0 |  |  | 0%
Porch - Screened |  |  | 0 |  |  | 0%
Deck - Composite |  |  | 0 |  |  | 0%
Deck - Wood |  |  | 0 |  |  | 0%
Fencing |  |  | 0 |  |  | 0%
Railings |  |  | 0 |  |  | 0%
Outdoor Built-Ins |  |  | 0 |  |  | 0%
Additional Structures |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
INSULATION + AIR SEALING | 0 | 0 | 0 |  |  | 0%
Air Sealing |  |  | 0 |  |  | 0%
Blower Door |  |  | 0 |  |  | 0%
Infrared |  |  | 0 |  |  | 0%
Insulation - Basement Interior |  |  | 0 |  |  | 0%
Insulation - Crawlspace |  |  | 0 |  |  | 0%
Insulation - Foam Board |  |  | 0 |  |  | 0%
Insulation - Roof / Attic |  |  | 0 |  |  | 0%
Insulation - Spray Foam |  |  | 0 |  |  | 0%
Insulation - Wall Cavity |  |  | 0 |  |  | 0%
Roof / Eave Baffles |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
PLUMBING | 0 | 0 | 0 |  |  | 0%
Drain |  |  | 0 |  |  | 0%
Waste |  |  | 0 |  |  | 0%
Vent |  |  | 0 |  |  | 0%
Piping - Water Supply |  |  | 0 |  |  | 0%
Piping - Gas |  |  | 0 |  |  | 0%
Water Heater |  |  | 0 |  |  | 0%
Water Treatment |  |  | 0 |  |  | 0%
Toilets |  |  | 0 |  |  | 0%
Tubs |  |  | 0 |  |  | 0%
Sinks |  |  | 0 |  |  | 0%
Showers |  |  | 0 |  |  | 0%
Faucets |  |  | 0 |  |  | 0%
Mixing Valves |  |  | 0 |  |  | 0%
Shower Heads |  |  | 0 |  |  | 0%
Disposal |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
ELECTRICAL | 0 | 0 | 0 |  |  | 0%
Service Panels |  |  | 0 |  |  | 0%
Sub-Panels |  |  | 0 |  |  | 0%
Rough Wiring |  |  | 0 |  |  | 0%
Phone / Cable / Internet Wiring |  |  | 0 |  |  | 0%
Lighting Fixtures |  |  | 0 |  |  | 0%
Low-Voltage Fixtures |  |  | 0 |  |  | 0%
Low-Voltage Transformers |  |  | 0 |  |  | 0%
Outlets |  |  | 0 |  |  | 0%
Switches |  |  | 0 |  |  | 0%
Dimmers |  |  | 0 |  |  | 0%
Lighting Control System |  |  | 0 |  |  | 0%
Doorbell |  |  | 0 |  |  | 0%
Smoke + CO2 Alarms |  |  | 0 |  |  | 0%
Intercom System |  |  | 0 |  |  | 0%
Security System |  |  | 0 |  |  | 0%
Home Theater |  |  | 0 |  |  | 0%
Home Entertainment System |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
HVAC | 0 | 0 | 0 |  |  | 0%
Air Handler |  |  | 0 |  |  | 0%
Boiler |  |  | 0 |  |  | 0%
Central AC |  |  | 0 |  |  | 0%
Ductwork |  |  | 0 |  |  | 0%
Furnace / Heat Pump |  |  | 0 |  |  | 0%
Grilles |  |  | 0 |  |  | 0%
HVAC Controls |  |  | 0 |  |  | 0%
Piping |  |  | 0 |  |  | 0%
Radiators |  |  | 0 |  |  | 0%
Registers |  |  | 0 |  |  | 0%
Solar Hot Water |  |  | 0 |  |  | 0%
Whole-House Ventilation |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
DRYWALL + PLASTER | 0 | 0 | 0 |  |  | 0%
Walls |  |  | 0 |  |  | 0%
Ceilings |  |  | 0 |  |  | 0%
Soffits |  |  | 0 |  |  | 0%
Decorative Plaster |  |  | 0 |  |  | 0%
Labor Costs |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
FINISH - INTERIOR | 0 | 0 | 0 |  |  | 0%
Built-In Cabinets |  |  | 0 |  |  | 0%
Built-In Shelving |  |  | 0 |  |  | 0%
Ceilings - Function |  |  | 0 |  |  | 0%
Ceilings - Decorative |  |  | 0 |  |  | 0%
Closet Hardware |  |  | 0 |  |  | 0%
Closet Shelving |  |  | 0 |  |  | 0%
Flooring - Carpet |  |  | 0 |  |  | 0%
Flooring - Tile / Stone Materials |  |  | 0 |  |  | 0%
Flooring - Tile / Stone Prep |  |  | 0 |  |  | 0%
Flooring - Vinyl |  |  | 0 |  |  | 0%
Flooring - Wood |  |  | 0 |  |  | 0%
Interior Door - Frames + Thresholds |  |  | 0 |  |  | 0%
Interior Door - Hardware |  |  | 0 |  |  | 0%
Interior Door - Prehung |  |  | 0 |  |  | 0%
Interior Door - Slabs |  |  | 0 |  |  | 0%
Interior Paint |  |  | 0 |  |  | 0%
Interior Stain |  |  | 0 |  |  | 0%
Paneling |  |  | 0 |  |  | 0%
Stairs / Railings / Newels |  |  | 0 |  |  | 0%
Wainscoting |  |  | 0 |  |  | 0%
Labor Costs |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
KITCHEN | 0 | 0 | 0 |  |  | 0%
Accessories |  |  | 0 |  |  | 0%
Backsplash |  |  | 0 |  |  | 0%
Built-ins |  |  | 0 |  |  | 0%
Cabinets |  |  | 0 |  |  | 0%
Cabinets - Hardware |  |  | 0 |  |  | 0%
Countertops |  |  | 0 |  |  | 0%
Shelving |  |  | 0 |  |  | 0%
Tile / Stone |  |  | 0 |  |  | 0%
Labor Costs |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
BATH | 0 | 0 | 0 |  |  | 0%
Accessories |  |  | 0 |  |  | 0%
Backsplash |  |  | 0 |  |  | 0%
Built-Ins |  |  | 0 |  |  | 0%
Cabinets |  |  | 0 |  |  | 0%
Cabinets - Hardware |  |  | 0 |  |  | 0%
Countertops |  |  | 0 |  |  | 0%
Medicine Cabinets |  |  | 0 |  |  | 0%
Mirrors |  |  | 0 |  |  | 0%
Raised Tub Platform |  |  | 0 |  |  | 0%
Shelving |  |  | 0 |  |  | 0%
Shower Enclosure |  |  | 0 |  |  | 0%
Tile / Stone |  |  | 0 |  |  | 0%
Tub Enclosure |  |  | 0 |  |  | 0%
Labor Costs |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
APPLIANCES | 0 | 0 | 0 |  |  | 0%
Cooktop |  |  | 0 |  |  | 0%
Deep Freeze |  |  | 0 |  |  | 0%
Dishwasher |  |  | 0 |  |  | 0%
Microwave Oven |  |  | 0 |  |  | 0%
Oven |  |  | 0 |  |  | 0%
Range Hood |  |  | 0 |  |  | 0%
Refrigerator |  |  | 0 |  |  | 0%
Washer + Dryer |  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
OTHER | 0 | 0 | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 0%
|  |  | 0 |  |  | 100%
CLICK HERE TO CREATE CONSTRUCTION ESTIMATING WORKSHEETS IN SMARTSHEET

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.