[](https://www.smartsheet.com/try-it?trp=11480&utm_source=integrated+content&utm_campaign=/content/six-sigma-project-charter&utm_medium=Nonprofit+Six+Sigma+Project+Charter+Example+doc+11480&lpa=Nonprofit+Six+Sigma+Project+Charter+Example+doc+11480&lx=PFpZZjisDNTS-Ddigi3MyABAgeTPLDIL8TQRu558b7w)**NONPROFIT SIX SIGMA PROJECT CHARTER**

**TEMPLATE EXAMPLE**

IMPORTANT REMINDER

A narrative written charter must be circulated and signed by the project sponsors. You can attach a completed version of this template to your narrative written charter to keep the charter short and concise.

Please make sure you meet with the project team and sponsors before completing this template. Much of the information required will need to come from a discussion with team members and sponsors.



GENERAL PROJECT INFORMATION

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| PROJECT NAME | | | PROJECT MANAGER | PROJECT SPONSOR |
| Summer Program Implementation | | |  |  |
| EMAIL | | PHONE | ORGANIZATIONAL UNIT | |
|  | | 000-000-0000 |  | |
| GREEN BELTS ASSIGNED |  |  | EXPECTED START DATE | EXPECTED COMPLETION DATE |
|  | | | 00/00/0000 | 00/00/0000 |
| BLACK BELTS ASSIGNED |  |  | EXPECTED SAVINGS | ESTIMATED COSTS |
|  | | | $237,750 | $184,900 |

PROJECT OVERVIEW

|  |  |
| --- | --- |
| PROBLEM  OR ISSUE | The New School Youth Program sees an opportunity to increase outreach to surrounding low-income schools and to expand its programming to a new age group. |
| PURPOSE  OF PROJECT | We aim to increase both the number of students reached and the number of participants in school-year programming. |
| BUSINESS  CASE | We will develop a feeder program in order to meet our strategic outreach goals. The New Age Jumpers is an elementary-age summer program targeting grades two through five. We will offer four week-long summer camps, attracting new participants from ten surrounding low-income schools. 25 percent of the summer programming participants will enroll in the year-long programming the following semester. |
| GOALS / METRICS | The summer program will enroll an average of 25 participants for each of the four week-long summer programs. Of those 100 participants, 25 will roll over into our school-year programming. |
| EXPECTED DELIVERABLES |  |

PROJECT SCOPE

|  |  |
| --- | --- |
| WITHIN  SCOPE | We will deliver the project in two phases. Summer programming is the scope of the first phase, which includes creating a core curriculum, marketing strategy, recruitment plan, and student assessment plan. |
| OUTSIDE  OF SCOPE | In the future, we will be partnering with other nonprofits and securing a corporate sponsor or grant funding. This is out of scope for the current project. |

TENTATIVE SCHEDULE

|  |  |  |
| --- | --- | --- |
| **KEY MILESTONE** | **START** | **FINISH** |
| Form Project Team and Conduct Preliminary Review |  |  |
| Finalize Project Plan and Project Charter |  |  |
| Conduct Definition Phase |  |  |
| Conduct Measurement Phase |  |  |
| Conduct Analysis Phase |  |  |
| Conduct Improvement Phase |  |  |
| Conduct Control Phase |  |  |
| Close Out Project and Write Summary Report |  |  |

RESOURCES

|  |  |
| --- | --- |
| PROJECT TEAM |  |
| SUPPORT RESOURCES |  |
| SPECIAL NEEDS |  |

COSTS

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **COST TYPE** | **VENDOR / LABOR NAMES** | | **RATE** | **QTY** | **AMOUNT** |
| **Labor** |  | | $150.00 | 200 | $ 30,000.00 |
| **Labor** |  | | $200.00 | 100 | $ 20,000.00 |
| **Labor** |  | | $350.00 | 50 | $ 17,500.00 |
| **Labor** |  | | $85,000.00 | 1 | $ 85,000.00 |
| **Labor** |  | | $4,850.00 | 3 | $ 14,550.00 |
| **Supplies** |  | | $17,850.00 | 1 | $ 17,850.00 |
|  |  |  | TOTAL COSTS | | $ 184,900.00 |

BENEFITS AND CUSTOMERS

|  |  |
| --- | --- |
| PROCESS OWNER |  |
| KEY STAKEHOLDERS |  |
| FINAL CUSTOMER |  |
| EXPECTED BENEFITS |  |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **TYPE OF BENEFIT** | **BASIS OF ESTIMATE** | | | **ESTIMATED BENEFIT AMOUNT** |
| **Specific Cost Savings** |  | | | $ 25,000.00 |
| **Enhanced Revenues** |  | | | $ 92,500.00 |
| **Higher Productivity (Soft)** |  | | | $ 17,500.00 |
| **Improved Compliance** |  | | | $ 12,000.00 |
| **Better Decision Making** |  | | | $ 18,500.00 |
| **Lower Maintenance Costs** |  | | | $ 26,000.00 |
| **Fewer Miscellaneous Costs** |  | | | $ 46,250.00 |
|  |  |  | TOTAL BENEFIT | $ 237,750.00 |

RISKS, CONSTRAINTS, AND ASSUMPTIONS

|  |  |
| --- | --- |
| RISKS |  |
| CONSTRAINTS |  |
| ASSUMPTIONS |  |

|  |  |  |
| --- | --- | --- |
| PREPARED BY | TITLE | DATE |
|  |  |  |

|  |
| --- |
| **DISCLAIMER**  Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk. |