## Requirement Mgmt Dashboard
REQUIREMENTS MANAGEMENT PLAN DASHBOARD TEMPLATE
PROJECT NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | 00/00/00 | ON TRACK | 72%
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Collect Requirements Management Plan Data | Alex B. | 2024-01-02 | 2024-01-08 | 7 | Complete | High
Define Requirements Activity Process | Frank C. | 2024-01-04 | 2024-01-11 | 8 | Complete | Medium
Communication Plan | Jacob S. | 2024-01-07 | 2024-01-11 | 5 | Complete | Low
Control Management Plan | Jacob S. | 2024-01-10 | 2024-01-15 | 6 | Complete | Low
Requirements Management Plan Document | Jacob S. | 2024-01-13 | 2024-01-20 | 8 | Complete | Low
Stakeholder Baselining | Alex B. | 2024-01-16 | 2024-01-29 | 14 | Overdue | High
Authorization | Frank C. | 2024-01-19 | 2024-02-01 | 14 | In Progress | High
Gather Requirements | Kennedy K. | 2024-01-22 | 2024-02-09 | 19 | In Progress | High
Analyze Requirements | Jacob S. | 2024-01-25 | 2024-02-05 | 12 | In Progress | High
Define Requirements | Alex B. | 2024-01-28 | 2024-02-06 | 10 | On Hold | High
Prioritize Requirements | Kennedy K. | 2024-01-31 | 2024-02-02 | 3 | Not Started | Medium
Validate & Maintain Requirements |  | 2024-02-03 | 2024-02-04 | 2 | Not Started | Medium
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 80000
Not Started | 2 | 16.67% |  | ACTUAL | 50000
In Progress | 3 | 25%
Complete | 5 | 41.67%
Overdue | 1 | 8.333%
On Hold | 1 | 8.333%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 6 | 50% |  | Actions | 2
Medium | 3 | 25% |  | Change Requests | 4
Low | 3 | 25%
TOTAL | 12 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Req. Mgmt Dashboard
REQUIREMENTS MANAGEMENT PLAN DASHBOARD
CAMPAIGN NAME |  |  |  | DATE | PROJECT STATUS | % COMPLETE
|  |  |  | 00/00/00 | ON TRACK | 100% | Enter DASHBOARD DATA in the tables beginning at row 8. Dashboard graphics will automatically populate.
TASK TIMELINE
DASHBOARD DATA
TASK TABLE
TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION in days | STATUS | PRIORITY | COMMENTS
Collect Requirements Management Plan Data |  |  |  | 0
Define Requirements Activity Process |  |  |  | 0
Communication Plan |  |  |  | 0
Control Management Plan |  |  |  | 0
Requirements Management Plan Document |  |  |  | 0
Stakeholder Baselining |  |  |  | 0
Authorization |  |  |  | 0
Gather Requirements |  |  |  | 0
Analyze Requirements |  |  |  | 0
Define Requirements |  |  |  | 0
Prioritize Requirements |  |  |  | 0
Validate & Maintain Requirements |  |  |  | 0
Task 13 |  |  |  | 0
Task 14 |  |  |  | 0
Task 15 |  |  |  | 0
Task 16 |  |  |  | 0
Task 17 |  |  |  | 0
Task 18 |  |  |  | 0
Task 19 |  |  |  | 0
Task 20 |  |  |  | 0
TASK STATUS % | automatically populates |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 0
Not Started | 0 |  |  | ACTUAL | 0
In Progress | 0
Complete | 0
Overdue | 0
On Hold | 0
TOTAL | 0 | 0%
TASK PRIORITY % | automatically populates |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 0 |  |  | Actions | 0
Medium | 0 |  |  | Change Requests | 0
Low | 0
0
TOTAL | 0 | 0%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - do not delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.