## EXAMPLE 3-Week Schedule
THREE-WEEK CONSTRUCTION SCHEDULE TEMPLATE
PROJECT NAME |  |  |  |  | PROJECT LOCATION
Project Alpha |  |  |  |  | Address, City, State ZIP | [6 empty] | WORK TYPE 1
PROJECT MANAGER |  |  |  |  | START DATE | [6 empty] | WORK TYPE 2
Henry McNeal |  |  |  |  | 2027-03-07 | [6 empty] | WORK TYPE 3
PROJECT NUMBER |  |  |  |  | END DATE | [6 empty] | WORK TYPE 4
001-ABC-DEF |  |  |  |  | 2027-03-28 | [6 empty] | PROJECT MILESTONE
PRE-CONSTRUCTION PHASE
ACTIVITY ID | ACTIVITY NAME | RESPONSIBLE PARTY | ORIGINAL DURATION | SUN | MON | TUES | WED | THUR | FRI | SAT | SUN | MON | TUES | WED | THUR | FRI | SAT | SUN | MON | TUES | WED | THUR | FRI | SAT | COMPLETION STATUS (BY PERCENT) | NOTES
|  |  |  | 2027-03-07 | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-13 | 2027-03-14 | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-20 | 2027-03-21 | 2027-03-22 | 2027-03-23 | 2027-03-24 | 2027-03-25 | 2027-03-26 | 2027-03-27
A10300 | Prepare/Submit Project Scheduler Qualifications | Henry McNeal | 3 | [21 empty] | 35 | bar: 2027-03-08 to 2027-03-11
A10301 | Prepare/Submit Insurance Certificates | Brent Williams | 5 | [21 empty] | 22 | bar: 2027-03-09 to 2027-03-12
A10302 | Prepare/Submit Preliminary Project Schedule | Henry McNeal | 5 | [21 empty] | 10 | bar: 2027-03-07; 2027-03-14 to 2027-03-15
A10303 | Prepare/Submit Quality Control Plan | Jason Desjardins | 3 | [21 empty] | 7 | bar: 2027-03-16 to 2027-03-19
A10304 | Review/Approve Health and Safety Plan | Jason Desjardins | 3 | [21 empty] | 80 | Contact SSHO Manager | bar: 2027-03-10 to 2027-03-12
A10305 | Review/Approve List of Proposed Contractors | Jason Desjardins | 5 | [21 empty] | 30 | bar: 2027-03-11 to 2027-03-15
A10305 | Mobilization |  | 0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK 3-Week Schedule
THREE-WEEK CONSTRUCTION SCHEDULE TEMPLATE
PROJECT NAME |  |  |  |  | PROJECT LOCATION
Name |  |  |  |  | Address, City, State ZIP | [6 empty] | WORK TYPE 1
PROJECT MANAGER |  |  |  |  | START DATE | [6 empty] | WORK TYPE 2
Name |  |  |  |  | 2027-03-07 | [6 empty] | WORK TYPE 3
PROJECT NUMBER |  |  |  |  | END DATE | [6 empty] | WORK TYPE 4
[5 empty] | 2027-03-28 |  | < The End Date will automatically populate 21 days ahead once the Start Date is entered. |  |  |  |  | PROJECT MILESTONE
PRE-CONSTRUCTION PHASE |  |  |  | Dates (MM/DD/YY) below will automatically populate beginning with the Start Date entered above. Days of the week need to be updated manually.
ACTIVITY ID | ACTIVITY NAME | RESPONSIBLE PARTY | ORIGINAL DURATION | SUN | MON | TUES | WED | THUR | FRI | SAT | SUN | MON | TUES | WED | THUR | FRI | SAT | SUN | MON | TUES | WED | THUR | FRI | SAT | COMPLETION STATUS (BY PERCENT) | NOTES
|  |  |  | 2027-03-07 | 2027-03-08 | 2027-03-09 | 2027-03-10 | 2027-03-11 | 2027-03-12 | 2027-03-13 | 2027-03-14 | 2027-03-15 | 2027-03-16 | 2027-03-17 | 2027-03-18 | 2027-03-19 | 2027-03-20 | 2027-03-21 | 2027-03-22 | 2027-03-23 | 2027-03-24 | 2027-03-25 | 2027-03-26 | 2027-03-27

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.