## SAMPLE - Strategic Project Plan
STRATEGIC PROJECT PLAN TEMPLATE
PROJECT NAME |  | PROJECT MANAGER | START | END | PROGRESS
Product Release |  | Alex B. | 2029-01-15 | 2029-04-20 | 35%
PROJECT DELIVERABLE
TASKS | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days
KICK-OFF |  |  | 2029-01-15 | 2029-01-21 | 7
Set kick-off meeting | Complete |  | 2029-01-15 | 2029-01-15 | 1
Agree on objectives | In Progress |  | 2029-01-16 | 2029-01-21 | 6
INITIATION |  |  | 2029-01-22 | 2029-02-25 | 35
Detailed Requirements | Not Started |  | 2029-01-22 | 2029-01-29 | 8
Hardware Requirements | Overdue |  | 2029-01-28 | 2029-01-31 | 4
Final Resource Plan | Needs Review |  | 2029-01-29 | 2029-02-25 | 28
Staffing | Approved |  | 2029-01-29 | 2029-02-25 | 28
DEVELOPMENT |  |  | 2029-02-28 | 2029-03-16 | 17
Technical Requirements | On Hold |  | 2029-02-28 | 2029-03-01 | 2
DB Development |  |  | 2029-02-28 | 2029-03-04 | 5
API Development |  |  | 2029-02-28 | 2029-03-04 | 5
UI Client |  |  | 2029-02-28 | 2029-03-04 | 5
Testing |  |  | 2029-02-28 | 2029-03-04 | 5
Dev. Complete |  |  | 2029-03-01 | 2029-03-16 | 16
OPERATIONS |  |  | 2029-03-16 | 2029-04-16 | 32
Hardware Configuration |  |  | 2029-03-16 | 2029-03-27 | 12
System Testing |  |  | 2029-03-28 | 2029-04-16 | 20
LAUNCH |  |  | 2029-04-20 | 2029-04-20 | 1
Strategic Alignment and Objectives
Strategic Goals Addressed | List the broader organizational or market goals that this project aims to support.
Expected Long-Term Outcomes | Describe the long-term benefits or impacts once the project is completed successfully.
Market Positioning | Describe how the project helps the organization in terms of competitive advantage or market positioning.
Risk and Opportunities | Discuss strategic risks and opportunities associated with the project and how they align with organizational risk appetite.
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Strategic Project Plan
STRATEGIC PROJECT PLAN TEMPLATE
PROJECT NAME |  | PROJECT MANAGER | START | END | PROGRESS
PROJECT DELIVERABLE
TASKS | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days
KICK-OFF
Task #1
Task #2
Task #3
Task #4
Task #5
INITIATION
Task #1
Task #2
Task #3
Task #4
Task #5
Task #6
DEVELOPMENT
Task #1
Task #2
Task #3
Task #4
Task #5
Task #6
OPERATIONS
Task #1
Task #2
Task #3
Task #4
Task #5
Task #6
LAUNCH
Task #1
Task #2
Task #3
Strategic Alignment and Objectives
Strategic Goals Addressed | List the broader organizational or market goals that this project aims to support.
Expected Long-Term Outcomes | Describe the long-term benefits or impacts once the project is completed successfully.
Market Positioning | Describe how the project helps the organization in terms of competitive advantage or market positioning.
Risk and Opportunities | Discuss strategic risks and opportunities associated with the project and how they align with organizational risk appetite.
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.