## BLANK - IT Infra Project Plan
IT INFRASTRUCTURE PROJECT PLAN
PROJECT NAME
TASK NAME | TASK OWNER | DURATION in days | START DATE | END DATE | STATUS | KEY RESOURCES / ADDITIONAL NOTES
Project Scope Phase |  |  |  | –
Gather background information |  |  |  | –
Define main priority |  |  |  | –
Define secondary priorities |  |  |  | –
Present system information: operating systems, current software version(s), and upgrading version(s) |  |  |  | –
Define project scope: upgrade and install new software on machines company-wide |  |  |  | –
Define roles and responsibilities |  |  |  | –
Assess risk |  |  |  | –
Define budget |  |  |  | –
Project Planning Phase |  |  |  | –
Create project timeline |  |  |  | –
Get project timeline approved |  |  |  | –
Design Phase |  |  |  | –
Define system information |  |  |  | –
Get additional technical specifications |  |  |  | –
Define how upgrade is expected to perform |  |  |  | –
Create installation plan |  |  |  | –
Alert organization of change and potential outages |  |  |  | –
Build and Test Phase |  |  |  | –
Acquire or create updated software |  |  |  | –
Build test plan |  |  |  | –
Execute test plan on small group of machines |  |  |  | –
Document any issues and test again |  |  |  | –
Finalize implementation plan |  |  |  | –
Deployment Phase |  |  |  | –
Install software upgrades according to plan |  |  |  | –
Document test performance, including any bugs or issues |  |  |  | –
Resolve bugs or issues |  |  |  | –
Alert organization of completion |  |  |  | –
Project Closeout |  |  |  | –
Review project goals and budget |  |  |  | –
Document overall success and learnings |  |  |  | –
Conduct project closeout meeting / huddle with IT team |  |  |  | –
Define ongoing maintenance schedule and roles and responsibilities |  |  |  | –
Continue maintenance |  |  |  | –
CLICK HERE TO CREATE IN SMARTSHEET
End Date will automatically
populate based upon Duration in Days and Start Date

## EX - IT Infra Project Plan
IT INFRASTRUCTURE PROJECT PLAN with Sample Data
PROJECT NAME
Company-Wise Software Update
TASK NAME | TASK OWNER | DURATION in days | START DATE | END DATE | STATUS | KEY RESOURCES / ADDITIONAL NOTES
Project Scope Phase |  |  |  | –
Gather background information | Vera Bowers | 2 | 2031-01-16 | 2031-01-17 | Complete | List any information on previous related projects and outdated infrastructure that this project will update.
Define main priority | Tamika Marshall | 1 | 2031-01-31 | 2031-01-31 | In Progress
Define secondary priorities | Suman Shine | 1 | 2031-02-05 | 2031-02-05 | Not Started
Present system information: operating systems, current software version(s), and upgrading version(s) | Sheldon Greene | 3 | 2031-01-31 | 2031-02-02 | Needs Review | Document the main systems, programs, or networks that your project will touch, and include information about their compatibility, lifespan, and constraints.
Define project scope: upgrade and install new software on machines company-wide | Sasha Petrov | 3 | 2031-02-05 | 2031-02-07 | Approved
Define roles and responsibilities | Sarah Goodwin | 2 | 2031-01-16 | 2031-01-17 | Overdue
Assess risk | Romy Bailey | 1 | 2031-01-31 | 2031-01-31 | On Hold
Define budget | Rolande Baghdasaryan | 10 | 2031-02-05 | 2031-02-14 |  | Include the costs for implementation and ongoing maintenance.
Project Planning Phase |  |  |  | –
Create project timeline | Raghu Prakash | 3 | 2031-01-22 | 2031-01-24 |  | Make sure to leave buffer time and budget for any foreseeable delays or ongoing maintenance checks.
Get project timeline approved | Petrus Nishimura | 2 | 2031-01-29 | 2031-01-30
Design Phase |  |  |  | –
Define system information | Patricia Hall | 3 | 2031-02-28 | 2031-03-02 |  | Indicate the specific programs you will be upgrading.
Get additional technical specifications | Olivia Carter | 2 | 2031-02-28 | 2031-03-01 |  | Address any other compatibility issues you need to get in front of before updating the software.
Define how upgrade is expected to perform | Mathias Nevin | 1 | 2031-03-01 | 2031-03-01
Create installation plan | Mateus Tobin | 1 | 2031-02-28 | 2031-02-28 |  | Include any potential outages or system issues that might occur during the installation.
Alert organization of change and potential outages | Marta Hicks | 1 | 2031-03-01 | 2031-03-01
Build and Test Phase |  |  |  | –
Acquire or create updated software | Lori Garcia | 15 | 2031-02-28 | 2031-03-14
Build test plan | Leigh Gibbs | 5 | 2031-02-28 | 2031-03-04
Execute test plan on small group of machines | Lazarus Barros | 1 | 2031-03-01 | 2031-03-01
Document any issues and test again | Krista Ahmed | 3 | 2031-02-28 | 2031-03-02
Finalize implementation plan | Kishore Kramer | 1 | 2031-03-01 | 2031-03-01
Deployment Phase |  |  |  | –
Install software upgrades according to plan | Kiran Gupta | 1 | 2031-03-16 | 2031-03-16
Document test performance, including any bugs or issues | Kelly Smart | 1 | 2031-03-18 | 2031-03-18
Resolve bugs or issues | Kassandra Hoover | 3 | 2031-03-18 | 2031-03-20
Alert organization of completion | Karl Peter | 1 | 2031-03-24 | 2031-03-24
Project Closeout |  |  |  | –
Review project goals and budget | Jose Price | 1 | 2031-03-24 | 2031-03-24
Document overall success and learnings | Jonathon Wong | 1 | 2031-03-26 | 2031-03-26
Conduct project closeout meeting / huddle with IT team | Jason Desjardins | 1 | 2031-03-24 | 2031-03-24
Define ongoing maintenance schedule and roles and responsibilities | Jamal King | 1 | 2031-03-26 | 2031-03-26
Continue maintenance | Isocrates Lombardi | 365 | 2031-04-06 | 2032-04-04 |  | Perform ongoing maintenance.
Formulas:
END DATE = IF(OR(ISBLANK([DURATION in days]),ISBLANK([START DATE])),"–",[DURATION in days]+[START DATE]-1)
End Date will automatically
populate based upon Duration in Days and Start Date

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.