## EXAMPLE Cross-Team RACI
Cross Team Collaboration RACI Matrix Template Example
Project Title |  |  |  | Project Manager | [11 empty] | Key Dates
Title |  |  |  | Name | [11 empty] | Dates
Project Description |  |  |  | Project Manager Contact Information
Description |  |  |  | Contact
|  |  | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5 | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5 | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5 | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5
PRIORITY | STATUS | PROJECT DELIVERABLE / ACTIVITY | Development |  |  |  |  | Quality (QA) |  |  |  |  | Marketing |  |  |  |  | Operations
PHASE 1
Low | In Progress | Identify Project Stakeholders (Operations) | R | C |  |  |  | R |  |  |  |  | C |  | R |  |  |  | A |  | R
Medium | Complete | Define Project Scope (Development) |  | A |  |  |  | I | [5 empty] | A |  |  | C
High | Needs Review | Develop Project Charter (Operations) |  |  | C |  |  |  | C | [8 empty] | I |  | C | C
| Approved | Appoint Project Team (Operations) |  |  |  | A |  |  |  | C | I |  |  |  |  | A | [5 empty] | A
| Not Started | Initial Risk Assessment (QA) |  |  |  |  | I |  |  | C |  |  | I |  | C |  |  |  | A
| Overdue | Set Preliminary Budget (Operations) | [7 empty] | C | [10 empty] | I | C
| On Hold | Stakeholder Meeting (Marketing) | [9 empty] | I | [9 empty] | C
PHASE 2
| Not Started | Create Work Breakdown Structure (WBS) (Development)
| Not Started | Develop Project Schedule (Operations)
| Not Started | Resource Allocation (Operations)
| Not Started | Risk Management Plan (QA)
| Not Started | Define Communication Plan (Marketing)
| Not Started | Budget Approval (Operations)
| Not Started | Set Up Project Management Tools (Development)
PHASE 3
| Not Started | Kickoff Meeting (Operations)
| Not Started | Develop Software Components (Development)
| Not Started | Conduct Regular Team Meetings (Operations)
| Not Started | Quality Assurance Testing (QA)
| Not Started | Performance Reporting (Operations)
| Not Started | Stakeholder Presentations (Marketing)
| Not Started | Implementation of Change Requests (Development)
PHASE 4
| Not Started | Track Project Performance (Operations)
| Not Started | Adjust Project Plans (Operations)
| Not Started | Quality Control Checks (QA)
| Not Started | Risk Monitoring (QA)
| Not Started | Budget Review (Operations)
| Not Started | Resource Reallocation (Operations)
| Not Started | Compliance Auditing (QA)
PHASE 5
| Not Started | Final Project Report (Operations)
| Not Started | Release Final Product (Development)
| Not Started | Conduct Post-Implementation Review (QA)
| Not Started | Close Out Budget (Operations)
| Not Started | Disband Project Team (Operations)
| Not Started | Document Lessons Learned (QA)
| Not Started | Celebrate Success (Marketing)
CLICK HERE TO CREATE IN SMARTSHEET
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## BLANK Cross-Team RACI
Cross Team Collaboration RACI Matrix Template
Project Title |  |  |  | Project Manager | [11 empty] | Key Dates
Project Description |  |  |  | Project Manager Contact Information
|  |  | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5 | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5 | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5 | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5
PRIORITY | STATUS | PROJECT DELIVERABLE / ACTIVITY | Team 1 |  |  |  |  | Team 2 |  |  |  |  | Team 3 |  |  |  |  | Team 4
PHASE 1
Low | In Progress | Activity 1
Medium | Complete | Activity 2
High | Needs Review
Approved
Not Started
Overdue
On Hold
PHASE 2
Activity 1
Activity 2
PHASE 3
Activity 1
Activity 2
PHASE 4
Activity 1
Activity 2
PHASE 5
Activity 1
Activity 2
RESPONSIBLE
ACCOUNTABLE
CONSULTED
INFORMED

## Dropdown Keys - Do Not Delete -
RACI DROPDOWN KEYS
– DO NOT DELETE –
| RACI KEY | PRIORITY | STATUS
R | Responsible | Low | Not Started
A | Accountable | Medium | In Progress
C | Consulted | High | Complete
I | Informed |  | Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.