## EXAMPLE - Approval Punch List
Approval Construction Punch List Template
This tab contains example data. To begin building your punch list, use the BLANK tab.
Project Name |  |  | Address |  |  | Project ID | Project Manager |  | Date
Approved By
[9 empty] | Engineer | Inspector | Owner | Contractor
Task ID | Task Description | Location | Status | Assigned To | Assigned By | Date Assigned | Date Due | Date Completed
1 | Replace roofing |  | Complete |  |  | 04/16/20XX | 05/13/20XX | 05/12/20XX | Y | Y | Y | Y
2 | Remove wall between living room and kitchen |  | Complete |  |  | 04/16/20XX | 04/24/20XX | 04/25/20XX | Y | Y | Y | Y
3 | Install double pane glass windows in bottom floor |  | Complete |  |  | 04/16/20XX | 04/30/20XX | 04/29/20XX | N | N | Y | Y
4 | Install new refrigerator |  | Complete |  |  | 04/25/20XX | 04/30/20XX | 04/30/20XX | N | N | Y | N
5 |  |  | In Progress
6 |  |  | Not Started
7 |  |  | Needs Review
8 |  |  | Approved
9 |  |  | On Hold
10 |  |  | Overdue
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Approval Punch List
Approval Construction Punch List Template
Project Name |  |  | Address |  |  | Project ID | Project Manager |  | Date
Approved By
[9 empty] | Engineer | Inspector | Owner | Contractor
Task ID | Task Description | Location | Status | Assigned To | Assigned By | Date Assigned | Date Due | Date Completed
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
Y / N | PRIORITY | STATUS
Y | Low | Not Started
N | Medium | In Progress
| High | Complete
| Urgent | Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.