## EXAMPLE - Construction Budget
Sample Monthly Construction Budget Template
This tab contains example data. To begin building your construction budget, use the BLANK tab.
Job Title |  |  |  | Project Manager
Oakwood Avenue Renovation |  |  |  | Mateus Tobin
Location |  |  |  | Start Date | End Date
1234 Oakwood Avenue, Anytown, USA |  |  |  | 01/15/20XX | 12/15/20XX
|  |  | Projected Subtotal | Actual Subtotal
|  | January | 33500 | 33700
|  | February | 60000 | 62300
|  | March | 75000 | 75500
|  | April | 98000 | 100500
|  | May | 47000 | 47500
|  | June | 56000 | 57000
|  | July | 3000 | 3000
|  | August | 2500 | 2700
|  | September | 1500 | 1500
|  | October | 2800 | 2900
|  | November | 7800 | 8500
|  | December | 3500 | 2850
–––––––––––––––– Budget ––––––––––––––––
|  |  | Projected Total | Actual Total | Variance
|  |  | 390600 | 397950 | 7350
Month | Project Phase | Task / Item | Projected Subtotal | Actual Subtotal | Variance | Party Responsible Vendor, Contractor, etc. | Status | Comments
January | Initial Planning & Approvals | Site Assessment | 4500 | 4200 | -300 |  | Complete | Environmental testing and land survey completed ahead of schedule.
January | Initial Planning & Approvals | Architectural Design | 15000 | 15000 | 0 |  | Complete | Finalized design for 5-story office building.
January | Initial Planning & Approvals | Permit Applications | 6000 | 6500 | 500 |  | Complete | Additional fee for expedited processing of permits.
January | Initial Planning & Approvals | Construction Insurance | 8000 | 8000 | 0 |  | Complete | Coverage includes builder’s risk and liability insurance.
February | Groundwork & Utilities Prep | Excavation and Grading | 20000 | 21500 | 1500 |  | Complete | Uncovered unexpected debris requiring additional labor.
February | Groundwork & Utilities Prep | Concrete Footings | 18000 | 17800 | -200 |  | Complete | Slightly reduced cost due to bulk materials discount.
February | Groundwork & Utilities Prep | Drainage Installation | 10000 | 10000 | 0 |  | Complete | Underground drainage system installed to prevent flooding.
February | Groundwork & Utilities Prep | Utility Hookups | 12000 | 13000 | 1000 |  | In Progress | Additional cost for sewer line relocation.
March | Structural Assembly | Steel Framing | 40000 | 39500 | -500 |  | Approved | Completed ahead of schedule, saving labor costs.
March | Structural Assembly | Reinforced Concrete Floors | 25000 | 25000 | 0 |  | Needs Review | Structural concrete floors poured for levels 1-3.
March | Structural Assembly | Elevator Shaft Construction | 10000 | 11000 | 1000 |  | Overdue | Adjustments made to meet updated safety codes.
April | Mechanical & Building Systems | HVAC System Installation | 50000 | 52000 | 2000 |  | On Hold | Upgraded to energy-efficient units, increasing initial cost.
April | Mechanical & Building Systems | Electrical Wiring | 30000 | 29000 | -1000 |  |  | Wiring completed for floors 1-3.
April | Mechanical & Building Systems | Plumbing Fixtures | 18000 | 19500 | 1500 |  |  | Minor changes in piping layout required additional materials.
May | Interior Development & Detailing | Drywall Installation | 20000 | 20000 | 0 |  |  | Completed on time, ready for painting.
May | Interior Development & Detailing | Painting | 15000 | 14500 | -500 |  |  | Negotiated lower cost for bulk paint purchase.
May | Interior Development & Detailing | Interior Glass Walls | 12000 | 13000 | 1000 |  |  | Additional costs for custom dimensions on conference rooms.
June | Exterior Enhancements & Landscaping | Exterior Landscaping | 25000 | 26500 | 1500 |  |  | Additional plants and irrigation installed to meet client specifications.
June | Exterior Enhancements & Landscaping | Parking Lot Paving | 18000 | 18000 | 0 |  |  | Parking lot completed with durable asphalt coating.
June | Exterior Enhancements & Landscaping | Final Inspections | 5000 | 5000 | 0 |  |  | Passed final building inspection with no major issues.
June | Exterior Enhancements & Landscaping | Cleaning and Handover | 8000 | 7500 | -500 |  |  | Reduced cost due to efficient cleaning schedule.
July |  |  | 3000 | 3000 | 0
August |  |  | 2500 | 2700 | 200
September |  |  | 1500 | 1500 | 0
October |  |  | 2800 | 2900 | 100
November |  |  | 7800 | 8500 | 700
December |  |  | 3500 | 2850 | -650
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Construction Budget
Monthly Construction Budget Template
Job Title |  |  |  | Project Manager
Location |  |  |  | Start Date | End Date
|  |  | Projected Subtotal | Actual Subtotal
|  | January | 0 | 0
|  | February | 0 | 0
|  | March | 0 | 0
|  | April | 0 | 0
|  | May | 0 | 0
|  | June | 0 | 0
|  | July | 0 | 0
|  | August | 0 | 0
|  | September | 0 | 0
|  | October | 0 | 0
|  | November | 0 | 0
|  | December | 0 | 0
–––––––––––––––– Budget ––––––––––––––––
|  |  | Projected Total | Actual Total | Variance
|  |  | 0 | 0 | 0
Month | Project Phase | Task / Item | Projected Subtotal | Actual Subtotal | Variance | Party Responsible Vendor, Contractor, etc. | Status | Comments
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS | MONTH
Yes | Low | Not Started | January
No | Medium | In Progress | February
| High | Complete | March
|  | Needs Review | April
|  | Approved | May
|  | Overdue | June
|  | On Hold | July
August
September
October
November
December

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.