## EXAMPLE - Construction Budget
Multi-Unit Construction Budget Template
This tab contains example data. To begin building your construction budget, use the BLANK tab.
Project Name |  | Number of Units | Date
Maplewood Apartments |  | 40 | Monday, February 28, 20XX
Location |  |  | Contractor
110-150 Maplewood Terrace, Anytown, USA
Multi-Unit Construction Budget | Site Square Footage | 120000
| Building Square Footage | 60000
| Total Square Footage | 180000
Sitework And Building Subtotal |  | 2365000
General Conditions | 5% | 118250
Insurance | 1.5% | 35475
Fees | 3% | 70950
Contingency | 7% | 165550
Total Expense |  | 2755225
On-Site Construction | Description | Cost | Notes
CONCRETE LABOR & MATERIALS
Foundation Excavation | Site prep and trench work | 30000
Concrete Footings | Pouring reinforced footings | 50000
Slab on Grade | Main floor concrete slabs | 80000
STRUCTURAL & OTHER METALS
Steel Framing | Support beams and columns | 120000
Metal Decking | Roof and floor decking | 40000
Rebar Installation | Reinforcement for concrete | 35000
CARPENTRY LABOR & MATERIALS
Wall Framing | Wood framing for walls | 150000
Floor Joists | Lumber for floor structure | 90000
Roof Framing | Trusses and supports | 70000
ROOFING, SIDING, & WATERPROOFING
Asphalt Shingle Roof | Installation of roofing | 60000
Waterproof Membrane | Basement waterproofing | 20000
Exterior Siding | Fiber cement siding panels | 75000
DOORS, WINDOWS, & HARDWARE
Entry Doors | Steel doors, fire-rated | 40000
Interior Doors | Pre-hung wooden doors | 30000
Windows | Energy efficient windows | 80000
WALL & FLOOR FINISHES
Drywall Installation | Includes tape and finish | 60000
Interior Paint | Two coats, all units | 40000
Flooring | LVP in units, tile in baths | 120000
PROJECT SPECIALTIES
Fire Protection System | Sprinklers throughout | 45000
Accessibility Compliance | ADA ramps and elevators | 15000
Signage | Interior and exterior signs | 10000
EQUIPMENT & APPLIANCES
Kitchen Appliances | Stoves, refrigerators | 80000
Water Heaters | Tankless systems | 50000
INTERIOR FURNISHINGS
Cabinets | Kitchens and bathrooms | 70000
Countertops | Granite countertops | 40000
Closet Shelving | Storage for all units | 20000
PLUMBING LABOR & MATERIALS
Rough-In Plumbing | Pipes for water/sewer lines | 80000
Fixtures | Sinks, toilets, tubs | 50000
Water Main Connection | Utility tie-in | 25000
HVAC LABOR & MATERIALS
Ductwork Installation |  | 60000
Air Quality Systems | Air filters and vents | 30000
HVAC Units | Includes furnaces/AC units | 100000
ELECTRICAL LABOR & MATERIALS
Electrical Rough-In |  | 80000
Light Fixtures | Interior and exterior lights | 40000
Panel Installation |  | 20000
ELEVATORS
Passenger Elevator | Main lobby installation | 100000
Elevator Maintenance | First-year service | 10000
Inspection and Testing | Compliance certification | 5000
PROFESSIONAL SERVICES & FEES
Architect Fees | Design and blueprint prep | 80000
Engineering Fees | Structural and civil design | 40000
Project Management | Oversite and scheduling | 60000
ADDITIONAL EXPENSES
Utilities Setup |  | 20000
Permitting Fees | City and county permits | 15000
FINAL CLEAN-UP
Site Cleanup | Debris removal | 10000
Interior Cleaning | Move-in ready cleaning | 15000
Waste Disposal | Dumpster removal | 5000
Total On-Site Costs |  | 2365000
Off-Site Construction | Description | Cost | Notes
CONCRETE LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
STRUCTURAL & OTHER METALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
CARPENTRY LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
ROOFING, SIDING, & WATERPROOFING
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
DOORS, WINDOWS, & HARDWARE
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
WALL & FLOOR FINISHES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
PROJECT SPECIALTIES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
EQUIPMENT & APPLIANCES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
INTERIOR FURNISHINGS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
PLUMBING LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
HVAC LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
ELECTRICAL LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
ELEVATORS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
PROFESSIONAL SERVICES & FEES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
ADDITIONAL EXPENSES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
FINAL CLEAN-UP
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
Total Off-Site Costs |  | 0
CLICK HERE TO CREATE IN SMARTSHEET
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO

## BLANK - Construction Budget
Multi-Unit Construction Budget Template
Project Name |  | Number of Units | Date
Location |  |  | Contractor
Multi-Unit Construction Budget | Site Square Footage
Building Square Footage
| Total Square Footage | 0
Sitework And Building Subtotal |  | 0
General Conditions | 0% | 0
Insurance | 0% | 0
Fees | 0% | 0
Contingency | 0% | 0
Total Expense |  | 0
On-Site Construction | Description | Cost | Notes
CONCRETE LABOR & MATERIALS
Foundation Excavation | Site prep and trench work
Concrete Footings | Pouring reinforced footings
Slab on Grade | Main floor concrete slabs
STRUCTURAL & OTHER METALS
Steel Framing | Support beams and columns
Metal Decking | Roof and floor decking
Rebar Installation | Reinforcement for concrete
CARPENTRY LABOR & MATERIALS
Wall Framing | Wood framing for walls
Floor Joists | Lumber for floor structure
Roof Framing | Trusses and supports
ROOFING, SIDING, & WATERPROOFING
Asphalt Shingle Roof | Installation of roofing
Waterproof Membrane | Basement waterproofing
Exterior Siding | Fiber cement siding panels
DOORS, WINDOWS, & HARDWARE
Entry Doors | Steel doors, fire-rated
Interior Doors | Pre-hung wooden doors
Windows | Energy efficient windows
WALL & FLOOR FINISHES
Drywall Installation | Includes tape and finish
Interior Paint | Two coats, all units
Flooring | LVP in units, tile in baths
PROJECT SPECIALTIES
Fire Protection System | Sprinklers throughout
Accessibility Compliance | ADA ramps and elevators
Signage | Interior and exterior signs
EQUIPMENT & APPLIANCES
Kitchen Appliances | Stoves, refrigerators
Water Heaters | Tankless systems
INTERIOR FURNISHINGS
Cabinets | Kitchens and bathrooms
Countertops | Granite countertops
Closet Shelving | Storage for all units
PLUMBING LABOR & MATERIALS
Rough-In Plumbing | Pipes for water/sewer lines
Fixtures | Sinks, toilets, tubs
Water Main Connection | Utility tie-in
HVAC LABOR & MATERIALS
Ductwork Installation
Air Quality Systems | Air filters and vents
HVAC Units | Includes furnaces/AC units
ELECTRICAL LABOR & MATERIALS
Electrical Rough-In
Light Fixtures | Interior and exterior lights
Panel Installation
ELEVATORS
Passenger Elevator | Main lobby installation
Elevator Maintenance | First-year service
Inspection and Testing | Compliance certification
PROFESSIONAL SERVICES & FEES
Architect Fees | Design and blueprint prep
Engineering Fees | Structural and civil design
Project Management | Oversite and scheduling
ADDITIONAL EXPENSES
Utilities Setup
Permitting Fees | City and county permits
FINAL CLEAN-UP
Site Cleanup | Debris removal
Interior Cleaning | Move-in ready cleaning
Waste Disposal | Dumpster removal
Total On-Site Costs |  | 0
Off-Site Construction | Description | Cost | Notes
CONCRETE LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
STRUCTURAL & OTHER METALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
CARPENTRY LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
ROOFING, SIDING, & WATERPROOFING
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
DOORS, WINDOWS, & HARDWARE
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
WALL & FLOOR FINISHES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
PROJECT SPECIALTIES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
EQUIPMENT & APPLIANCES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
INTERIOR FURNISHINGS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
PLUMBING LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
HVAC LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
ELECTRICAL LABOR & MATERIALS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
ELEVATORS
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
PROFESSIONAL SERVICES & FEES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
ADDITIONAL EXPENSES
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
FINAL CLEAN-UP
[ITEMIZED TASK/MATERIAL 1]
[ITEMIZED TASK/MATERIAL 2]
[ITEMIZED TASK/MATERIAL 3]
Total Off-Site Costs |  | 0
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
YES
UNKNOWN
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO
NO

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.