## EXAMPLE Comm Construct Time
Commercial Construction Timeline Template Example
Project Location | [5 empty] | Start Date
789 Valley Avenue, Weller, PA | [5 empty] | 2035-03-04 | <--Enter the date of the first Sunday in your project timeline to populate the schedule.
Project Manager | [5 empty] | End Date
Romy Bailey | [5 empty] | MM/DD/YY
WBS | Task Name | Assigned To | Start Date | Finish Date | Duration in days | Percentage Complete | 2035-03-04 | [6 empty] | 2035-03-11 | [6 empty] | 2035-03-18 | [6 empty] | 2035-03-25 | [6 empty] | 2035-04-01 | [6 empty] | 2035-04-08 | [6 empty] | 2035-04-15 | [6 empty] | 2035-04-22 | [6 empty] | 2035-04-29 | [6 empty] | 2035-05-06 | [6 empty] | 2035-05-13 | [6 empty] | 2035-05-20 | [6 empty] | 2035-05-27 | [6 empty] | 2035-06-03 | [6 empty] | 2035-06-10 | [6 empty] | 2035-06-17 | [6 empty] | 2035-06-24 | [6 empty] | 2035-07-01 | [6 empty] | 2035-07-08 | [6 empty] | 2035-07-15 | [6 empty] | 2035-07-22 | [6 empty] | 2035-07-29 | [6 empty] | 2035-08-05 | [6 empty] | 2035-08-12 | [6 empty] | 2035-08-19 | [6 empty] | 2035-08-26 | [6 empty] | 2035-09-02 | [6 empty] | 2035-09-09
[7 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
1 | Phase 1: Pre-Construction | Lori Garcia | 2035-03-05 | 2035-03-16 | 12 | 61.25%
1.1 | Purchase Vacant Lot | Romy Bailey | 2035-03-05 | 2035-03-13 | 9 | 100% | bar: 2035-03-04 M to 2035-03-11 T
1.2 | Site Survey | Romy Bailey | 2035-03-07 | 2035-03-10 | 4 | 85% | bar: 2035-03-04 T to 2035-03-04 F
1.3 | Soil Testing | Denis Vidal | 2035-03-14 | 2035-03-16 | 3 | 50% | bar: 2035-03-11 M to 2035-03-11 W
1.4 | Outline the Project Scope | Denis Vidal | 2035-03-14 | 2035-03-16 | 3 | 10% | bar: 2035-03-11 W to 2035-03-11 F
1.4.1 | Timeline | bar: 2035-03-11 W to 2035-03-11 F
1.4.2 | Budget | bar: 2035-03-11 W to 2035-03-11 F
1.5 | Cost Analysis
1.6 | Assemble Team
1.6.1 | Hire Architect and Engineer
1.6.2 | Hire Design Team
1.6.3 | Hire Contractors
1.7 | Initial Design Plans
1.7.1 | Engineering Assessment
1.8 | Bill of Materials
1.9 | Blueprints and Specifications
1.1 | Agreements
1.11 | Contracts
1.12 | Permit Acquisition
1.13 | Zoning
1.14 | Land Use Approvals
1.15 | Environmental Impact Assessment
1.16 | Finalize Design Plans
2 | Phase 2: Procurement and Bidding
2.1 | Determine Materials, Equipment, and Services
2.2 | Develop a Procurement Plan
2.3 | Identify Supplier(s)
2.4 | Send RFQs
2.5 | Evaluate Bids
2.6 | Choose Supplier(s)
2.7 | Order Materials
2.8 | Schedule Deliveries
3 | Phase 3: Site Prep
3.1 | Survey Results
3.1.1 | Site Survey
3.1.2 | Elevation Survey
3.2 | Cost Analysis
3.2.1 | Site Prep Costs
3.2.2 | Utility Accessibility
3.3 | Utility Accessibility
3.4 | Stake Property Lines
3.4.1 | Mark Property Boundaries
3.4.2 | Establish Setbacks and Building Envelope
3.5 | Clearing and Excavation
3.6 | Leveling
3.6.1 | Remove or Add Soils
3.6.2 | Compact Soil
3.6.3 | Add Drainage
4 | Phase 4: Construction
4.1 | Foundation
4.2 | Framing
4.3 | Roofing
4.4 | Windows
4.5 | Plumbing
4.6 | Electrical
4.7 | HVAC
4.8 | Ventilation System
4.9 | Fire Suppression System
4.1 | Elevators
4.11 | Escalators
4.12 | Insulation
4.13 | Drywall
4.14 | Interior Paint
4.15 | Doors
4.16 | Cabinetry
4.17 | Countertops
4.18 | Trim and Molding
4.19 | Lighting
4.2 | Flooring
4.20.1 | Tile
4.20.2 | Hardwood
4.20.3 | Carpet
4.20.4 | Stone
4.21 | Hardware
4.22 | Mirrors
4.23 | Specialized Equipment
4.24 | Appliances
4.25 | Exterior Finishes
4.25.1 | Siding
4.25.2 | Gutters
4.25.3 | Paint
4.25.4 | Trim
4.25.5 | Masonry
4.26 | Data Wiring
4.27 | Deck, Patio, Balcony
4.28 | Swimming Pool
4.29 | Sidewalks and ADA Ramps
4.3 | Parking Lot
4.31 | Signage
4.32 | Landscaping
5 | Phase 5: Post-Construction
5.1 | Final Inspection
5.2 | Punch List
5.3 | Final Clean-Up
5.4 | Final Walkthrough
5.5 | Handover
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2035-03-04 Su to 2035-03-25 Sa
TODAY

## BLANK Comm Construct Timeline
Commercial Construction Timeline Template
Project Location | [5 empty] | Start Date
[6 empty] | 2035-03-04 | <--Enter the date of the first Sunday in your project timeline to populate the schedule.
Project Manager | [5 empty] | End Date
MM/DD/YY
WBS | Task Name | Assigned To | Start Date | Finish Date | Duration in days | Percentage Complete | 2035-03-04 | [6 empty] | 2035-03-11 | [6 empty] | 2035-03-18 | [6 empty] | 2035-03-25 | [6 empty] | 2035-04-01 | [6 empty] | 2035-04-08 | [6 empty] | 2035-04-15 | [6 empty] | 2035-04-22 | [6 empty] | 2035-04-29 | [6 empty] | 2035-05-06 | [6 empty] | 2035-05-13 | [6 empty] | 2035-05-20 | [6 empty] | 2035-05-27 | [6 empty] | 2035-06-03 | [6 empty] | 2035-06-10 | [6 empty] | 2035-06-17 | [6 empty] | 2035-06-24 | [6 empty] | 2035-07-01 | [6 empty] | 2035-07-08 | [6 empty] | 2035-07-15 | [6 empty] | 2035-07-22 | [6 empty] | 2035-07-29 | [6 empty] | 2035-08-05 | [6 empty] | 2035-08-12 | [6 empty] | 2035-08-19 | [6 empty] | 2035-08-26 | [6 empty] | 2035-09-02 | [6 empty] | 2035-09-09
[7 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
1 | Phase 1: Pre-Construction | Name | 2035-03-05 | 2035-03-13 | 9 | 61.25%
1.1 | Purchase Vacant Lot | Name | 2035-03-05 | 2035-03-13 | 9 | 100% | bar: 2035-03-04 M to 2035-03-11 T
1.2 | Site Survey |  |  |  |  | 85% | bar: 2035-03-04 T to 2035-03-04 F
1.3 | Soil Testing |  |  |  |  | 50% | bar: 2035-03-11 M to 2035-03-11 W
1.4 | Outline the Project Scope |  |  |  |  | 10% | bar: 2035-03-11 W to 2035-03-11 F
1.4.1 | Timeline | bar: 2035-03-11 W to 2035-03-11 F
1.4.2 | Budget | bar: 2035-03-11 W to 2035-03-11 F
1.5 | Cost Analysis
1.6 | Assemble Team
1.6.1 | Hire Architect and Engineer
1.6.2 | Hire Design Team
1.6.3 | Hire Contractors
1.7 | Initial Design Plans
1.7.1 | Engineering Assessment
1.8 | Bill of Materials
1.9 | Blueprints and Specifications
1.1 | Agreements
1.11 | Contracts
1.12 | Permit Acquisition
1.13 | Zoning
1.14 | Land Use Approvals
1.15 | Environmental Impact Assessment
1.16 | Finalize Design Plans
2 | Phase 2: Procurement and Bidding
2.1 | Determine Materials, Equipment, and Services
2.2 | Develop a Procurement Plan
2.3 | Identify Supplier(s)
2.4 | Send RFQs
2.5 | Evaluate Bids
2.6 | Choose Supplier(s)
2.7 | Order Materials
2.8 | Schedule Deliveries
3 | Phase 3: Site Prep
3.1 | Survey Results
3.1.1 | Site Survey
3.1.2 | Elevation Survey
3.2 | Cost Analysis
3.2.1 | Site Prep Costs
3.2.2 | Utility Accessibility
3.3 | Utility Accessibility
3.4 | Stake Property Lines
3.4.1 | Mark Property Boundaries
3.4.2 | Establish Setbacks and Building Envelope
3.5 | Clearing and Excavation
3.6 | Leveling
3.6.1 | Remove or Add Soils
3.6.2 | Compact Soil
3.6.3 | Add Drainage
4 | Phase 4: Construction
4.1 | Foundation
4.2 | Framing
4.3 | Roofing
4.4 | Windows
4.5 | Plumbing
4.6 | Electrical
4.7 | HVAC
4.8 | Ventilation System
4.9 | Fire Suppression System
4.1 | Elevators
4.11 | Escalators
4.12 | Insulation
4.13 | Drywall
4.14 | Interior Paint
4.15 | Doors
4.16 | Cabinetry
4.17 | Countertops
4.18 | Trim and Molding
4.19 | Lighting
4.2 | Flooring
4.20.1 | Tile
4.20.2 | Hardwood
4.20.3 | Carpet
4.20.4 | Stone
4.21 | Hardware
4.22 | Mirrors
4.23 | Specialized Equipment
4.24 | Appliances
4.25 | Exterior Finishes
4.25.1 | Siding
4.25.2 | Gutters
4.25.3 | Paint
4.25.4 | Trim
4.25.5 | Masonry
4.26 | Data Wiring
4.27 | Deck, Patio, Balcony
4.28 | Swimming Pool
4.29 | Sidewalks and ADA Ramps
4.3 | Parking Lot
4.31 | Signage
4.32 | Landscaping
5 | Phase 5: Post-Construction
5.1 | Final Inspection
5.2 | Punch List
5.3 | Final Clean-Up
5.4 | Final Walkthrough
5.5 | Handover
TODAY

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.