## EXAMPLE Construction KPI Dash
Construction Project KPI Dashboard Template Example
Construction Project | Skyline Apartments
Reporting Period | September 1, 20XX – November 30, 20XX
Project Status | At Risk
Percentage Complete | 40%
KPI | Definition | Target | Current Value | Status | Trend
Cost Variance (CV) | Difference between budgeted and actual costs | 0 | -10000 | Critical | Declining
Schedule Variance (SV) | Difference between planned and actual schedule performance | 0 days | +5 days | At Risk | Stable
Tasks Completed on Time | Percentage of tasks finished by their deadlines | 90% | 85% | At Risk | Declining
Labor Utilization Rate | Percentage of labor resources actively in use | 85% | 80% | At Risk | Stable
Safety Incident Rate | Number of incidents per 1,000 hours worked | 0 | 1 | Critical | Inclining
Material Delivery Timeliness | Percentage of materials delivered on schedule | 95% | 92% | On Track | Stable
Project Progress | Percentage of the project completed | 45% | 40% | At Risk | Declining
Change Request Impact | Number of changes affecting the schedule/budget | ≤2 | 3 | Critical | Inclining
Equipment Utilization | Percentage of equipment actively in use | 90% | 88% | On Track | Stable
Budget Usage
KPI | Target | Current Value | Percentage of Total
Labor Costs | 200000 | 180000 | 36%
Material Costs | 250000 | 230000 | 46%
Equipment Costs | 100000 | 90000 | 18%
Monthly Schedule Variance
KPI | September | October | November
Planned Progress | 15% | 30% | 45%
Actual Progress | 12% | 25% | 40%
Cost Overruns
Month | Planned Cost | Actual Cost | Variance ($)
September | 50000 | 55000 | -5000
October | 100000 | 110000 | -10000
November | 150000 | 160000 | -10000
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Construction KPI Dash
Construction Project KPI Dashboard Template
Construction Project
Reporting Period
Project Status
Percentage Complete
KPI | Definition | Target | Current Value | Status | Trend
|  |  |  | Critical | Declining
|  |  |  | At Risk | Stable
|  |  |  | At Risk | Declining
|  |  |  | At Risk | Stable
|  |  |  | Critical | Inclining
|  |  |  | On Track | Stable
|  |  |  | At Risk | Declining
|  |  |  | Critical | Inclining
|  |  |  | On Track | Stable
Budget Usage
KPI | Target | Current Value | Percentage of Total
Labor Costs | 0 | 0 | 0%
Material Costs | 0 | 0 | 0%
Equipment Costs | 0 | 0 | 0%
Monthly Schedule Variance
KPI | September | October | November
Planned Progress | 0% | 0% | 0%
Actual Progress | 0% | 0% | 0%
Cost Overruns
Month | Planned Cost | Actual Cost | Variance ($)
September | 0 | 0 | 0
October | 0 | 0 | 0
November | 0 | 0 | 0

## Key - DO NOT DELETE
Dropdown Key - Do Not Delete
| Status | Trend
| On Track | Stable
| At Risk | Declining
| Critical | Inclining

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.