## EXAMPLE Res Construct Timeline
Residential Construction Timeline Template Example
Project Location | [5 empty] | Start Date
123 Main Street, Valley View, PA | [5 empty] | 2028-01-05 | <--Enter the date of the first Sunday in your project timeline to populate the schedule.
Project Manager | [5 empty] | Expected End Date
Lori Garcia | [5 empty] | MM/DD/YY
WBS | Task Name | Assigned To | Start Date | Finish Date | Duration in days | Percentage Complete | 2028-01-05 | [6 empty] | 2028-01-12 | [6 empty] | 2028-01-19 | [6 empty] | 2028-01-26 | [6 empty] | 2028-02-02 | [6 empty] | 2028-02-09 | [6 empty] | 2028-02-16 | [6 empty] | 2028-02-23 | [6 empty] | 2028-03-01 | [6 empty] | 2028-03-08 | [6 empty] | 2028-03-15 | [6 empty] | 2028-03-22 | [6 empty] | 2028-03-29 | [6 empty] | 2028-04-05 | [6 empty] | 2028-04-12 | [6 empty] | 2028-04-19 | [6 empty] | 2028-04-26 | [6 empty] | 2028-05-03 | [6 empty] | 2028-05-10 | [6 empty] | 2028-05-17 | [6 empty] | 2028-05-24 | [6 empty] | 2028-05-31 | [6 empty] | 2028-06-07 | [6 empty] | 2028-06-14 | [6 empty] | 2028-06-21 | [6 empty] | 2028-06-28 | [6 empty] | 2028-07-05 | [6 empty] | 2028-07-12
[7 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
1 | Phase 1: Pre-Construction | Lori Garcia | 2028-01-06 | 2028-01-17 | 12 | 61.25%
1.1 | Purchase Vacant Lot | Romy Bailey | 2028-01-06 | 2028-01-14 | 9 | 100% | bar: 2028-01-05 M to 2028-01-12 T
1.2 | Site Survey | Romy Bailey | 2028-01-07 | 2028-01-10 | 4 | 85% | bar: 2028-01-05 T to 2028-01-05 F
1.3 | Soil Testing | Denis Vidal | 2028-01-13 | 2028-01-15 | 3 | 50% | bar: 2028-01-12 M to 2028-01-12 W
1.4 | Budget Estimation | Denis Vidal | 2028-01-15 | 2028-01-17 | 3 | 10% | bar: 2028-01-12 W to 2028-01-12 F
1.5 | Cost Analysis
1.6 | Hire Architect or Engineer
1.7 | Hire Design Team
1.8 | Hire Contractors
1.9 | Initial Design Plans
1.1 | Bill of Materials
1.11 | Blueprints
1.12 | Agreements
1.13 | Contracts
1.14 | Permit Acquisition
1.15 | Finalize Design Plans
2 | Phase 2: Procurement
2.1 | Determine Materials, Equipment, and Services
2.2 | Develop a Procurement Plan
2.3 | Identify Supplier(s)
2.4 | Send RFQs
2.5 | Evaluate Bids
2.6 | Choose Supplier(s)
2.7 | Order Materials
2.8 | Schedule Deliveries
3 | Phase 3: Site Prep
3.1 | Survey Results
3.1.1 | Site Survey
3.1.2 | Elevation Survey
3.2 | Cost Analysis
3.2.1 | Site Prep Costs
3.2.2 | Utility Accessibility
3.3 | Utility Accessibility
3.4 | Stake Property Lines
3.4.1 | Mark Property Boundaries
3.4.2 | Establish Setbacks and Building Envelope
3.5 | Clearing and Excavation
3.6 | Leveling
3.6.1 | Remove or Add Soils
3.6.2 | Compact Soil
3.6.3 | Add Drainage
4 | Phase 4: Construction
4.1 | Foundation
4.2 | Framing
4.3 | Roofing
4.4 | Windows
4.5 | Plumbing
4.6 | Electrical
4.7 | HVAC
4.8 | Insulation
4.9 | Drywall
4.1 | Interior Paint
4.11 | Doors
4.12 | Cabinetry
4.13 | Countertops
4.14 | Trim and Molding
4.15 | Lighting
4.16 | Flooring
4.16.1 | Tile
4.16.2 | Hardwood
4.16.3 | Carpet
4.16.4 | Stone
4.17 | Hardware
4.18 | Mirrors
4.19 | Appliances
4.2 | Exterior Finishes
4.20.1 | Siding
4.20.2 | Gutters
4.20.3 | Paint
4.20.4 | Trim
4.20.5 | Masonry
4.21 | Deck, Patio, Porch
4.22 | Driveway and Sidewalks
4.23 | Fencing
5 | Phase 5: Post-Construction
5.1 | Final Inspection
5.2 | Punch List
5.3 | Final Clean-Up
5.4 | Final Walkthrough
5.5 | Handover
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2028-01-05 Su to 2028-01-26 Sa
TODAY

## BLANK Res Construct Timeline
Residential Construction Timeline Template
Project Location | [5 empty] | Start Date
Address | [5 empty] | 2028-01-05 | <--Enter the date of the first Sunday in your project timeline to populate the schedule.
Project Manager | [5 empty] | Expected End Date
Name | [5 empty] | MM/DD/YY
WBS | Task Name | Assigned To | Start Date | Finish Date | Duration in days | Percentage Complete | 2028-01-05 | [6 empty] | 2028-01-12 | [6 empty] | 2028-01-19 | [6 empty] | 2028-01-26 | [6 empty] | 2028-02-02 | [6 empty] | 2028-02-09 | [6 empty] | 2028-02-16 | [6 empty] | 2028-02-23 | [6 empty] | 2028-03-01 | [6 empty] | 2028-03-08 | [6 empty] | 2028-03-15 | [6 empty] | 2028-03-22 | [6 empty] | 2028-03-29 | [6 empty] | 2028-04-05 | [6 empty] | 2028-04-12 | [6 empty] | 2028-04-19 | [6 empty] | 2028-04-26 | [6 empty] | 2028-05-03 | [6 empty] | 2028-05-10 | [6 empty] | 2028-05-17 | [6 empty] | 2028-05-24 | [6 empty] | 2028-05-31 | [6 empty] | 2028-06-07 | [6 empty] | 2028-06-14 | [6 empty] | 2028-06-21 | [6 empty] | 2028-06-28 | [6 empty] | 2028-07-05 | [6 empty] | 2028-07-12
[7 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
1 | Phase 1: Pre-Construction | Name | 2028-01-06 | 2028-01-14 | 9 | 61.25%
1.1 | Purchase Vacant Lot | Name | 2028-01-06 | 2028-01-14 | 9 | 100% | bar: 2028-01-05 M to 2028-01-12 T
1.2 | Site Survey | Name |  |  |  | 85% | bar: 2028-01-05 T to 2028-01-05 F
1.3 | Soil Testing | Name |  |  |  | 50% | bar: 2028-01-12 M to 2028-01-12 W
1.4 | Budget Estimation | Name |  |  |  | 10% | bar: 2028-01-12 W to 2028-01-12 F
1.5 | Cost Analysis
1.6 | Hire Architect or Engineer
1.7 | Hire Design Team
1.8 | Hire Contractors
1.9 | Initial Design Plans
1.1 | Bill of Materials
1.11 | Blueprints
1.12 | Agreements
1.13 | Contracts
1.14 | Permit Acquisition
1.15 | Finalize Design Plans
2 | Phase 2: Procurement
2.1 | Determine Materials, Equipment, and Services
2.2 | Develop a Procurement Plan
2.3 | Identify Supplier(s)
2.4 | Send RFQs
2.5 | Evaluate Bids
2.6 | Choose Supplier(s)
2.7 | Order Materials
2.8 | Schedule Deliveries
3 | Phase 3: Site Prep
3.1 | Survey Results
3.1.1 | Site Survey
3.1.2 | Elevation Survey
3.2 | Cost Analysis
3.2.1 | Site Prep Costs
3.2.2 | Utility Accessibility
3.3 | Utility Accessibility
3.4 | Stake Property Lines
3.4.1 | Mark Property Boundaries
3.4.2 | Establish Setbacks and Building Envelope
3.5 | Clearing and Excavation
3.6 | Leveling
3.6.1 | Remove or Add Soils
3.6.2 | Compact Soil
3.6.3 | Add Drainage
4 | Phase 4: Construction
4.1 | Foundation
4.2 | Framing
4.3 | Roofing
4.4 | Windows
4.5 | Plumbing
4.6 | Electrical
4.7 | HVAC
4.8 | Insulation
4.9 | Drywall
4.1 | Interior Paint
4.11 | Doors
4.12 | Cabinetry
4.13 | Countertops
4.14 | Trim and Molding
4.15 | Lighting
4.16 | Flooring
4.16.1 | Tile
4.16.2 | Hardwood
4.16.3 | Carpet
4.16.4 | Stone
4.17 | Hardware
4.18 | Mirrors
4.19 | Appliances
4.2 | Exterior Finishes
4.20.1 | Siding
4.20.2 | Gutters
4.20.3 | Paint
4.20.4 | Trim
4.20.5 | Masonry
4.21 | Deck, Patio, Porch
4.22 | Driveway and Sidewalks
4.23 | Fencing
5 | Phase 5: Post-Construction
5.1 | Final Inspection
5.2 | Punch List
5.3 | Final Clean-Up
5.4 | Final Walkthrough
5.5 | Handover
TODAY

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.