## EXAMPLE 2-Week Schedule
Two-Week Look Ahead Construction Schedule Template
PROJECT NAME |  |  |  |  | PROJECT LOCATION
Project Alpha |  |  |  |  | Address, City, State ZIP | [6 empty] | WORK TYPE 1
PROJECT MANAGER |  |  |  |  | START DATE | [6 empty] | WORK TYPE 2
Henry McNeal |  |  |  |  | 2035-03-02 | [6 empty] | WORK TYPE 3
PROJECT NUMBER |  |  |  |  | END DATE | [6 empty] | WORK TYPE 4
001-ABC-DEF |  |  |  |  | 2035-03-16 |  | < End Date will automatically populate 14 days ahead once the Start Date is entered.
PRE-CONSTRUCTION PHASE
ACTIVITY ID | ACTIVITY NAME | RESPONSIBLE PARTY | ORIGINAL DURATION | SUN | MON | TUES | WED | THUR | FRI | SAT | SUN | MON | TUES | WED | THUR | FRI | SAT | COMPLETION STATUS (BY PERCENT) | NOTES
A10300 | Prepare/Submit Project Scheduler Qualifications | Henry McNeal | 3 | [14 empty] | 35 | bar: MON to THUR
A10301 | Prepare/Submit Insurance Certificates | Brent Williams | 5 | [14 empty] | 22 | bar: TUES to FRI
A10302 | Prepare/Submit Preliminary Project Schedule | Henry McNeal | 5 | [14 empty] | 10 | bar: SUN; SUN to MON
A10303 | Prepare/Submit Quality Control Plan | Jason Desjardins | 3 | [14 empty] | 7 | bar: TUES to FRI
A10304 | Review/Approve Health and Safety Plan | Jason Desjardins | 3 | [14 empty] | 80 | Contact SSHO Manager | bar: WED to FRI
A10305 | Review/Approve List of Proposed Contractors | Jason Desjardins | 5 | [14 empty] | 30 | bar: THUR to MON
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK 2-Week Schedule
TWO-WEEK CONSTRUCTION SCHEDULE TEMPLATE
PROJECT NAME |  |  |  |  | PROJECT LOCATION
Name |  |  |  |  | Address, City, State ZIP | [6 empty] | WORK TYPE 1
PROJECT MANAGER |  |  |  |  | START DATE | [6 empty] | WORK TYPE 2
Name |  |  |  |  | 2035-03-02 | [6 empty] | WORK TYPE 3
PROJECT NUMBER |  |  |  |  | END DATE | [6 empty] | WORK TYPE 4
0 |  |  |  |  | 2035-03-16 |  | < End Date will automatically populate 14 days ahead once the Start Date is entered.
PRE-CONSTRUCTION PHASE
ACTIVITY ID | ACTIVITY NAME | RESPONSIBLE PARTY | ORIGINAL DURATION | SUN | MON | TUES | WED | THUR | FRI | SAT | SUN | MON | TUES | WED | THUR | FRI | SAT | COMPLETION STATUS (BY PERCENT) | NOTES
35
22
10
7
80
30

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.