## Slide 1
Notes for Using This Template
Phasing Slide: Enter the phasing data and details that represent your plan and process. Adjust phasing fields on the next slide to suit your plan.
Implementation Slide: Enter Project Tasks in the chart area. Enter Label Owners in the key below the chart. Adjust bars to represent the length of time per task. Add Start and End Dates, Due Dates, Milestone Dates, or additional Task Information within each bar or in the chart area.
Basic Implementation Plan Presentation Template Example

## Slide 2
Phase 1
Phase 2
Phase 3
Phase 4
Survey potential locations for charging stations.
Feasibility Study
Design and Development
Conduct a market analysis to identify target customer segment.
Estimate initial investment and potential ROI.
Additional details …
Finalize designs for charging stations and accompanying infrastructure.
Develop software solutions for payment, station monitoring, and user interface.
Secure required permits and approvals for installation.
Additional details …
Identify a limited region for pilot installation.
Collect user feedback on station performance and usability.
Address any technical glitches or challenges identified during the pilot.
Additional details …
Launch marketing campaigns targeting potential users.
Begin phased installation of charging stations across targeted regions.
Train personnel on station maintenance and customer support.
Additional details …
Pilot Testing
Full-Scale Rollout
Example

## Slide 3
Tasks | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Feasibility Study |  |  |  |  |  | 
Design and Development |  |  |  |  |  | 
Pilot Testing |  |  |  |  |  | 
Full-Scale Rollout |  |  |  |  |  | 
Operational Management |  |  |  |  |  | 
Customer Engagement and Support |  |  |  |  |  | 
Performance Review and Optimization |  |  |  |  |  | 
Expansion and Growth |  |  |  |  |  | 
Research New Markets |  |  |  |  |  | 
Implement Upgrades |  |  |  |  |  | 
Due 00/00
Due 00/00
Milestone 1
Needs Review
Due 00/00
Due 00/00
Due 00/00
Due 00/00
Due 00/00
Henry McNeal, Project Manager
Lori Garcia, Sr. Project Manager
Paul Finley, Assistant Project Manager
Sasha Petrov, Assistant Project Manager
Devon Gomez, Quality Control
Sylvie Beasley, Operations
Bruce Ferguson, Operations
Bindy Peterson, Outreach
TODAY
Milestone 1 – 00/00
Due 00/00
Example

## Slide 4
Phase 1
Phase 2
Phase 3
Phase 4
Description
Phase Title
Phase Title
Description
Description
Description
Description
Description
Description
Description
Phase Title
Phase Title
Description
Description
Description
Description
Description
Description
Description
Description

## Slide 5
Tasks | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6
Task 1 |  |  |  |  |  | 
Task 2 |  |  |  |  |  | 
Due 00/00
Due 00/00
Milestone 1
Needs Review
Due 00/00
Due 00/00
Due 00/00
Due 00/00
Due 00/00
Name, Title
Name, Title
Name, Title
Name, Title
Name, Title
Name, Title
Name, Title
Name, Title
TODAY
Milestone 1 – 00/00
Due 00/00
Provided by Smartsheet, Inc.

## Slide 6
DISCLAIMER Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.