## Slide 1
New Hire Onboarding Plan Template Example
Employee | Krista Ahmed
Job Title | Marketing Analyst
Department | Marketing
Hiring Manager | Leigh Gibbs
Start Date | MM/DD/YY
Remote / In-Office Status | Hybrid (3 days in-office, 2 days remote)

## Slide 2
Preboarding Phase |  | 
Objective | Description | 
Prepare employee for their first day. | Ensure they have all necessary tools, paperwork, and company information. | 
Establish a positive first impression. | Send a welcome email, introduce key contacts, and provide preboarding resources. | 
Set up necessary systems. | IT and HR should ensure that technology, payroll, and system access are ready. | 
Role | Responsibility | 
Information Technology | Set up email, laptop, software access, and accounts. | 
Hiring Manager | Assign a mentor, prepare a first-week schedule, and inform the team. | 
Buddy or Mentor | Introduce yourself, share valuable resources, and be available for questions. | 

## Slide 3
Orientation Phase |  | 
Objective | Description | 
Familiarize employee with company culture. | Introduce mission, values, and key policies. | 
Provide structured training. | Set clear job expectations and start onboarding modules. | 
Encourage engagement and connection. | Help the employee build relationships within the team. | 
Timeframe | Key Focus Area | Owner
First day | Welcome session, IT setup, office tour | HR, IT, Manager
First week | Job expectations, team intros, training | Manager
End of week one | Check-in with manager and buddy | Manager, Buddy

## Slide 4
Integration Phase |  | 
Timeframe | Objective | Description
30 days | Understand initial role. | Complete job training.
60 days | Increase ownership. | Take on tasks; seek peer feedback.
90 days | Fully integrate into the company. | Performance review; discuss goals.
Timeframe | Milestones | Owner
30 days | Understand role responsibilities; complete training and initial performance check-in. | Manager
60 days | Increase ownership of tasks; receive peer feedback; continue development. | Manager, HR
90 days | Conduct performance review; discuss goals; assess onboarding experience. | Manager, HR

## Slide 5
Next Steps (Beyond 90 Days) |  | 
Goal | Actions | Owner
Continued professional development | Assign additional training, mentorship, or learning resources. | Manager
Career growth planning | Set short-term and long-term career goals. | Manager, Employee
First formal performance review | Conduct a six-month or one-year review. | HR, Manager
Provided by Smartsheet, Inc.

## Slide 6
DISCLAIMER Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.