## EXAMPLE - Construction Budget
Restaurant Construction Budget Example
–––––––––––––––– Budget ––––––––––––––––
|  | Estimated Total | Actual Total | Difference Total
|  | 265169 | 290746 | 25577
WBS | Category & Items | Estimated | Actual | Difference
1.0 | General Requirements | 12255 | 14309 | 2054
1.1 | Plans & Permits | 5007 | 5217 | 210
1.2 | Administrative Costs | 3142 | 3409 | 267
1.3 | Financing & Legal Fees | 3096 | 3092 | -4
1.4 | Other | 1010 | 2591 | 1581
1.5 |  |  |  | 0
1.6 |  |  |  | 0
1.7 |  |  |  | 0
1.8 |  |  |  | 0
1.9 |  |  |  | 0
1.10 |  |  |  | 0
2.0 | Site Preparation | 25147 | 28012 | 2865
2.1 | Space Remodel & Improvements | 18543 | 19987 | 1444
2.2 | Dumpster & Waste Removal | 2452 | 3102 | 650
2.3 | Job-Site Security & Storage | 1297 | 1784 | 487
2.4 | Temporary Utilities & Rentals | 2120 | 1850 | -270
2.5 | Other | 735 | 1289 | 554
2.6 |  |  |  | 0
2.7 |  |  |  | 0
2.8 |  |  |  | 0
2.9 |  |  |  | 0
2.10 |  |  |  | 0
2.11 |  |  |  | 0
2.12 |  |  |  | 0
2.13 |  |  |  | 0
3.0 | Utilities and Infrastructure | 28925 | 32217 | 3292
3.1 | Plumbing System Updates | 6431 | 7842 | 1411
3.2 | Electrical System Updates | 7452 | 8490 | 1038
3.3 | Gas Line Installation/Updates | 3420 | 3125 | -295
3.4 | Telecom & Internet Setup | 2102 | 2450 | 348
3.5 | HVAC System Modifications | 8650 | 9020 | 370
3.6 | Other | 870 | 1290 | 420
3.7 |  |  |  | 0
3.8 |  |  |  | 0
3.9 |  |  |  | 0
3.10 |  |  |  | 0
4.0 | Interior Construction | 47567 | 52094 | 4527
4.1 | Flooring (Tile, Vinyl, Wood) | 10645 | 11432 | 787
4.2 | Walls & Ceiling Finishes | 8421 | 9230 | 809
4.3 | Painting & Staining | 4231 | 5110 | 879
4.4 | Interior Doors & Hardware | 3740 | 3520 | -220
4.5 | Lighting Fixtures & Setup | 6230 | 6812 | 582
4.6 | Furniture & Fixtures Install | 12430 | 13780 | 1350
4.7 | Other | 1870 | 2210 | 340
4.8 |  |  |  | 0
4.9 |  |  |  | 0
4.10 |  |  |  | 0
4.11 |  |  |  | 0
4.12 |  |  |  | 0
4.13 |  |  |  | 0
4.14 |  |  |  | 0
4.15 |  |  |  | 0
5.0 | Kitchen and Service Areas | 71965 | 76370 | 4405
5.1 | Stainless Steel Workstations | 8231 | 8752 | 521
5.2 | Walk-in & Refrigeration Setup | 15642 | 16234 | 592
5.3 | Cooking Equipment Installation | 25132 | 26041 | 909
5.4 | Dishwashing Station Setup | 7234 | 8121 | 887
5.5 | Prep Areas & Storage Setup | 8541 | 9250 | 709
5.6 | Fire Suppression System | 5420 | 5872 | 452
5.7 | Other | 1765 | 2100 | 335
5.8 |  |  |  | 0
5.9 |  |  |  | 0
5.10 |  |  |  | 0
5.11 |  |  |  | 0
5.12 |  |  |  | 0
5.13 |  |  |  | 0
5.14 |  |  |  | 0
5.15 |  |  |  | 0
5.16 |  |  |  | 0
5.17 |  |  |  | 0
5.18 |  |  |  | 0
5.19 |  |  |  | 0
6.0 | Dining Area and Bar | 46219 | 50897 | 4678
6.1 | Bar Setup & Counters | 13654 | 14930 | 1276
6.2 | Seating & Tables | 17450 | 18952 | 1502
6.3 | POS & Payment System Setup | 7540 | 8215 | 675
6.4 | Signage & Branding | 5230 | 6120 | 890
6.5 | Other | 2345 | 2680 | 335
6.6 |  |  |  | 0
6.7 |  |  |  | 0
6.8 |  |  |  | 0
6.9 |  |  |  | 0
6.10 |  |  |  | 0
6.11 |  |  |  | 0
6.12 |  |  |  | 0
6.13 |  |  |  | 0
6.14 |  |  |  | 0
6.15 |  |  |  | 0
6.16 |  |  |  | 0
6.17 |  |  |  | 0
6.18 |  |  |  | 0
6.19 |  |  |  | 0
6.20 |  |  |  | 0
7.0 | Exterior and Accessibility | 33091 | 36847 | 3756
7.1 | Signage & Exterior Paint | 7100 | 8240 | 1140
7.2 | Outdoor Seating & Fencing | 9231 | 10232 | 1001
7.3 | Parking Lot & Walkways | 6340 | 6790 | 450
7.4 | ADA Compliance Upgrades | 8230 | 9110 | 880
7.5 | Other | 2190 | 2475 | 285
7.6 |  |  |  | 0
7.7 |  |  |  | 0
7.8 |  |  |  | 0
7.9 |  |  |  | 0
7.10 |  |  |  | 0
7.11 |  |  |  | 0
7.12 |  |  |  | 0
7.13 |  |  |  | 0
7.14 |  |  |  | 0
7.15 |  |  |  | 0
7.16 |  |  |  | 0
7.17 |  |  |  | 0
7.18 |  |  |  | 0
7.19 |  |  |  | 0
8.0 | Other | 0 | 0 | 0
8.1 |  |  |  | 0
8.2 |  |  |  | 0
8.3 |  |  |  | 0
8.4 |  |  |  | 0
8.5 |  |  |  | 0
8.6 |  |  |  | 0
8.7 |  |  |  | 0
8.8 |  |  |  | 0
8.9 |  |  |  | 0
8.10 |  |  |  | 0
8.11 |  |  |  | 0
8.12 |  |  |  | 0
8.13 |  |  |  | 0
8.14 |  |  |  | 0
8.15 |  |  |  | 0
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Construction Budget
Restaurant Construction Budget
–––––––––––––––– Budget ––––––––––––––––
|  | Estimated Total | Actual Total | Difference Total
|  | 0 | 0 | 0
WBS | Category & Items | Estimated | Actual | Difference
1.0 | General Requirements | 0 | 0 | 0
1.1 |  | 0 | 0 | 0
1.2 |  | 0 | 0 | 0
1.3 |  | 0 | 0 | 0
1.4 |  | 0 | 0 | 0
1.5 |  |  |  | 0
1.6 |  |  |  | 0
1.7 |  |  |  | 0
1.8 |  |  |  | 0
1.9 |  |  |  | 0
1.10 |  |  |  | 0
2.0 | Site Preparation | 0 | 0 | 0
2.1 |  | 0 |  | 0
2.2 |  |  |  | 0
2.3 |  |  |  | 0
2.4 |  |  |  | 0
2.5 |  |  |  | 0
2.6 |  |  |  | 0
2.7 |  |  |  | 0
2.8 |  |  |  | 0
2.9 |  |  |  | 0
2.10 |  |  |  | 0
2.11 |  |  |  | 0
2.12 |  |  |  | 0
2.13 |  |  |  | 0
3.0 | Utilities and Infrastructure | 0 | 0 | 0
3.1 |  |  |  | 0
3.2 |  |  |  | 0
3.3 |  |  |  | 0
3.4 |  |  |  | 0
3.5 |  |  |  | 0
3.6 |  |  |  | 0
3.7 |  |  |  | 0
3.8 |  |  |  | 0
3.9 |  |  |  | 0
3.10 |  |  |  | 0
4.0 | Interior Construction | 0 | 0 | 0
4.1 |  |  |  | 0
4.2 |  |  |  | 0
4.3 |  |  |  | 0
4.4 |  |  |  | 0
4.5 |  |  |  | 0
4.6 |  |  |  | 0
4.7 |  |  |  | 0
4.8 |  |  |  | 0
4.9 |  |  |  | 0
4.10 |  |  |  | 0
4.11 |  |  |  | 0
4.12 |  |  |  | 0
4.13 |  |  |  | 0
4.14 |  |  |  | 0
4.15 |  |  |  | 0
5.0 | Kitchen and Service Areas | 0 | 0 | 0
5.1 |  |  |  | 0
5.2 |  |  |  | 0
5.3 |  |  |  | 0
5.4 |  |  |  | 0
5.5 |  |  |  | 0
5.6 |  |  |  | 0
5.7 |  |  |  | 0
5.8 |  |  |  | 0
5.9 |  |  |  | 0
5.10 |  |  |  | 0
5.11 |  |  |  | 0
5.12 |  |  |  | 0
5.13 |  |  |  | 0
5.14 |  |  |  | 0
5.15 |  |  |  | 0
5.16 |  |  |  | 0
5.17 |  |  |  | 0
5.18 |  |  |  | 0
5.19 |  |  |  | 0
6.0 | Dining Area and Bar | 0 | 0 | 0
6.1 |  |  |  | 0
6.2 |  |  |  | 0
6.3 |  |  |  | 0
6.4 |  |  |  | 0
6.5 |  |  |  | 0
6.6 |  |  |  | 0
6.7 |  |  |  | 0
6.8 |  |  |  | 0
6.9 |  |  |  | 0
6.10 |  |  |  | 0
6.11 |  |  |  | 0
6.12 |  |  |  | 0
6.13 |  |  |  | 0
6.14 |  |  |  | 0
6.15 |  |  |  | 0
6.16 |  |  |  | 0
6.17 |  |  |  | 0
6.18 |  |  |  | 0
6.19 |  |  |  | 0
6.20 |  |  |  | 0
7.0 | Exterior and Accessibility | 0 | 0 | 0
7.1 |  |  |  | 0
7.2 |  |  |  | 0
7.3 |  |  |  | 0
7.4 |  |  |  | 0
7.5 |  |  |  | 0
7.6 |  |  |  | 0
7.7 |  |  |  | 0
7.8 |  |  |  | 0
7.9 |  |  |  | 0
7.10 |  |  |  | 0
7.11 |  |  |  | 0
7.12 |  |  |  | 0
7.13 |  |  |  | 0
7.14 |  |  |  | 0
7.15 |  |  |  | 0
7.16 |  |  |  | 0
7.17 |  |  |  | 0
7.18 |  |  |  | 0
7.19 |  |  |  | 0
8.0 | Other | 0 | 0 | 0
8.1 |  |  |  | 0
8.2 |  |  |  | 0
8.3 |  |  |  | 0
8.4 |  |  |  | 0
8.5 |  |  |  | 0
8.6 |  |  |  | 0
8.7 |  |  |  | 0
8.8 |  |  |  | 0
8.9 |  |  |  | 0
8.10 |  |  |  | 0
8.11 |  |  |  | 0
8.12 |  |  |  | 0
8.13 |  |  |  | 0
8.14 |  |  |  | 0
8.15 |  |  |  | 0

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.