## Construction Project WBS
Construction Project WBS Template Example
Project Title | Company Name
Project Manager | Date
CLICK HERE TO CREATE IN SMARTSHEET
Construction Project
Define Project
Hold specification meetings
Develop PM deliverables
Detailed Design & Tender
Construction
Project Close/Post Project
Project drawings
Schedule of prev completed work
Elements checklist
Project brief & business case
Project plan & generic cost plan
Submit end stage report
Tender for main asbestos removal & install
Enable works design & tender
Select contractors
Submit end stage report
Switch off heat
Certify all areas clear
Contractor mobilization
Remove asbestos
Re-install all areas
New install
Proceed with non-destructive testing
Make sure deliverables coincide with small works manual
Submit end stage report
Obtain approval to close project
Contractor demobilization

## Construction Project WBS-BLANK
Construction Project WBS Template
Project Title | Company Name
Project Manager | Date

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.