## EXAMPLE Construction Schedule
Residential Construction Schedule Template Example
Project Name |  | Client Name
Project Beta |  | Romy Bailey
Site Address | [5 empty] | Start Date
123 Main Street, Valley View, PA | [5 empty] | 2028-01-05 | <--Enter the date of the first Sunday in your project timeline to populate the schedule.
Project Manager | [5 empty] | Estimated Completion
Lori Garcia | [5 empty] | MM/DD/YY
Status | Task / Phase Name | Assigned To | Start Date | End Date | Duration in days | Percentage Complete | 2028-01-05 | [6 empty] | 2028-01-12 | [6 empty] | 2028-01-19 | [6 empty] | 2028-01-26 | [6 empty] | 2028-02-02 | [6 empty] | 2028-02-09 | [6 empty] | 2028-02-16 | [6 empty] | 2028-02-23 | [6 empty] | 2028-03-01 | [6 empty] | 2028-03-08 | [6 empty] | 2028-03-15 | [6 empty] | 2028-03-22 | [6 empty] | 2028-03-29 | [6 empty] | 2028-04-05 | [6 empty] | 2028-04-12 | [6 empty] | 2028-04-19 | [6 empty] | 2028-04-26 | [6 empty] | 2028-05-03 | [6 empty] | 2028-05-10 | [6 empty] | 2028-05-17 | [6 empty] | 2028-05-24 | [6 empty] | 2028-05-31 | [6 empty] | 2028-06-07 | [6 empty] | 2028-06-14 | [6 empty] | 2028-06-21 | [6 empty] | 2028-06-28 | [6 empty] | 2028-07-05 | [6 empty] | 2028-07-12
[7 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
In Progress | Phase 1: Pre-Construction | Lori Garcia | 2028-01-06 | 2028-01-17 | 12 | 61.25%
Complete | Purchase Vacant Lot | Romy Bailey | 2028-01-06 | 2028-01-14 | 9 | 100% | bar: 2028-01-05 M to 2028-01-12 T
In Progress | Site Survey | Romy Bailey | 2028-01-07 | 2028-01-10 | 4 | 85% | bar: 2028-01-05 T to 2028-01-05 F
In Progress | Soil Testing | Denis Vidal | 2028-01-13 | 2028-01-15 | 3 | 50% | bar: 2028-01-12 M to 2028-01-12 W
In Progress | Budget Estimation | Denis Vidal | 2028-01-15 | 2028-01-17 | 3 | 10% | bar: 2028-01-12 W to 2028-01-12 F
Not Started | Cost Analysis
Not Started | Hire Architect or Engineer
Not Started | Hire Design Team
Not Started | Hire Contractors
Not Started | Initial Design Plans
Not Started | Bill of Materials
Not Started | Blueprints
Not Started | Agreements
Not Started | Contracts
Not Started | Permit Acquisition
Not Started | Finalize Design Plans
Not Started | Phase 2: Procurement
Not Started | Determine Materials, Equipment, and Services
Not Started | Develop a Procurement Plan
Not Started | Identify Supplier(s)
Not Started | Send RFQs
Not Started | Evaluate Bids
Not Started | Choose Supplier(s)
Not Started | Order Materials
Not Started | Schedule Deliveries
Not Started | Phase 3: Site Prep
Not Started | Survey Results
Not Started | Site Survey
Not Started | Elevation Survey
Not Started | Cost Analysis
Not Started | Site Prep Costs
Not Started | Utility Accessibility
Not Started | Utility Accessibility
Not Started | Stake Property Lines
Not Started | Mark Property Boundaries
Not Started | Establish Setbacks and Building Envelope
Not Started | Clearing and Excavation
Not Started | Leveling
Not Started | Remove or Add Soils
Not Started | Compact Soil
Not Started | Add Drainage
Not Started | Phase 4: Construction
Not Started | Foundation
Not Started | Framing
Not Started | Roofing
Not Started | Windows
Not Started | Plumbing
Not Started | Electrical
Not Started | HVAC
Not Started | Insulation
Not Started | Drywall
Not Started | Interior Paint
Not Started | Doors
Not Started | Cabinetry
Not Started | Countertops
Not Started | Trim and Molding
Not Started | Lighting
Not Started | Flooring
Not Started | Tile
Not Started | Hardwood
Not Started | Carpet
Not Started | Stone
Not Started | Hardware
Not Started | Mirrors
Not Started | Appliances
Not Started | Exterior Finishes
Not Started | Siding
Not Started | Gutters
Not Started | Paint
Not Started | Trim
Not Started | Masonry
Not Started | Deck, Patio, Porch
Not Started | Driveway and Sidewalks
Not Started | Fencing
Not Started | Phase 5: Post-Construction
Not Started | Final Inspection
Not Started | Punch List
Not Started | Final Clean-Up
Not Started | Final Walkthrough
Not Started | Handover
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2028-01-05 Su to 2028-01-26 Sa
TODAY

## BLANK Construction Schedule
Residential Construction Schedule Template
Project Name |  | Client Name
Site Address | [5 empty] | Start Date
[6 empty] | 2028-01-05 | <--Enter the date of the first Sunday in your project timeline to populate the schedule.
Project Manager | [5 empty] | Estimated Completion
MM/DD/YY
Status | Task / Phase Name | Assigned To | Start Date | End Date | Duration in days | Percentage Complete | 2028-01-05 | [6 empty] | 2028-01-12 | [6 empty] | 2028-01-19 | [6 empty] | 2028-01-26 | [6 empty] | 2028-02-02 | [6 empty] | 2028-02-09 | [6 empty] | 2028-02-16 | [6 empty] | 2028-02-23 | [6 empty] | 2028-03-01 | [6 empty] | 2028-03-08 | [6 empty] | 2028-03-15 | [6 empty] | 2028-03-22 | [6 empty] | 2028-03-29 | [6 empty] | 2028-04-05 | [6 empty] | 2028-04-12 | [6 empty] | 2028-04-19 | [6 empty] | 2028-04-26 | [6 empty] | 2028-05-03 | [6 empty] | 2028-05-10 | [6 empty] | 2028-05-17 | [6 empty] | 2028-05-24 | [6 empty] | 2028-05-31 | [6 empty] | 2028-06-07 | [6 empty] | 2028-06-14 | [6 empty] | 2028-06-21 | [6 empty] | 2028-06-28 | [6 empty] | 2028-07-05 | [6 empty] | 2028-07-12
[7 empty] | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa | Su | M | T | W | R | F | Sa
In Progress | Phase 1: Pre-Construction |  | 2028-01-06 | 2028-01-14 | 9 | 61.25%
Complete | Purchase Vacant Lot |  | 2028-01-06 | 2028-01-14 | 9 | 100% | bar: 2028-01-05 M to 2028-01-12 T
In Progress | Site Survey |  |  |  |  | 85% | bar: 2028-01-05 T to 2028-01-05 F
In Progress | Soil Testing |  |  |  |  | 50% | bar: 2028-01-12 M to 2028-01-12 W
In Progress | Budget Estimation |  |  |  |  | 10% | bar: 2028-01-12 W to 2028-01-12 F
Not Started | Cost Analysis
Not Started | Hire Architect or Engineer
Not Started | Hire Design Team
Not Started | Hire Contractors
Not Started | Initial Design Plans
Not Started | Bill of Materials
Not Started | Blueprints
Not Started | Agreements
Not Started | Contracts
Not Started | Permit Acquisition
Not Started | Finalize Design Plans
Not Started | Phase 2: Procurement
Not Started | Determine Materials, Equipment, and Services
Not Started | Develop a Procurement Plan
Not Started | Identify Supplier(s)
Not Started | Send RFQs
Not Started | Evaluate Bids
Not Started | Choose Supplier(s)
Not Started | Order Materials
Not Started | Schedule Deliveries
Not Started | Phase 3: Site Prep
Not Started | Survey Results
Not Started | Site Survey
Not Started | Elevation Survey
Not Started | Cost Analysis
Not Started | Site Prep Costs
Not Started | Utility Accessibility
Not Started | Utility Accessibility
Not Started | Stake Property Lines
Not Started | Mark Property Boundaries
Not Started | Establish Setbacks and Building Envelope
Not Started | Clearing and Excavation
Not Started | Leveling
Not Started | Remove or Add Soils
Not Started | Compact Soil
Not Started | Add Drainage
Not Started | Phase 4: Construction
Not Started | Foundation
Not Started | Framing
Not Started | Roofing
Not Started | Windows
Not Started | Plumbing
Not Started | Electrical
Not Started | HVAC
Not Started | Insulation
Not Started | Drywall
Not Started | Interior Paint
Not Started | Doors
Not Started | Cabinetry
Not Started | Countertops
Not Started | Trim and Molding
Not Started | Lighting
Not Started | Flooring
Not Started | Tile
Not Started | Hardwood
Not Started | Carpet
Not Started | Stone
Not Started | Hardware
Not Started | Mirrors
Not Started | Appliances
Not Started | Exterior Finishes
Not Started | Siding
Not Started | Gutters
Not Started | Paint
Not Started | Trim
Not Started | Masonry
Not Started | Deck, Patio, Porch
Not Started | Driveway and Sidewalks
Not Started | Fencing
Not Started | Phase 5: Post-Construction
Not Started | Final Inspection
Not Started | Punch List
Not Started | Final Clean-Up
Not Started | Final Walkthrough
Not Started | Handover
TODAY

## Status Key - Do Not Delete
Dropdown Keys - Do Not Delete
Status
Not Started
In Progress
Complete

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.