## Residential Renovation Timeline
Residential Remodel Project Timeline Template
Project Name |  | Project Manager |  |  | Start Date
Project Name |  | Name |  |  | 2035-09-20 | <--Enter date of Monday of first week. Schedule will auto-populate.
PRIORITY | TASK NAME | START DATE | END DATE | DURATION | STATUS | PERCENTAGE COMPLETE | ASSIGNED TO | COMMENTS | 2035-09-20 |  |  |  |  | 2035-09-27 |  |  |  |  | 2035-10-04 |  |  |  |  | 2035-10-11 |  |  |  |  | 2035-10-18 |  |  |  |  | 2035-10-25 |  |  |  |  | 2035-11-01 |  |  |  |  | 2035-11-08 |  |  |  |  | 2035-11-15 |  |  |  |  | 2035-11-22 |  |  |  |  | 2035-11-29 |  |  |  |  | 2035-12-06 |  |  |  |  | 2035-12-13 |  |  |  |  | 2035-12-20 |  |  |  |  | 2035-12-27 |  |  |  |  | 2036-01-03 |  |  |  |  | 2036-01-10 |  |  |  |  | 2036-01-17 |  |  |  |  | 2036-01-24 |  |  |  |  | 2036-01-31 |  |  |  |  | 2036-02-07 |  |  |  |  | 2036-02-14 |  |  |  |  | 2036-02-21 |  |  |  |  | 2036-02-28 |  |  |  |  | 2036-03-06 |  |  |  |  | 2036-03-13 |  |  |  |  | 2036-03-20 |  |  |  |  | 2036-03-27 |  |  |  |  | 2036-04-03 |  |  |  |  | 2036-04-10 |  |  |  |  | 2036-04-17 |  |  |  |  | 2036-04-24 |  |  |  |  | 2036-05-01 |  |  |  |  | 2036-05-08 |  |  |  |  | 2036-05-15 |  |  |  |  | 2036-05-22 |  |  |  |  | 2036-05-29 |  |  |  |  | 2036-06-05 |  |  |  |  | 2036-06-12 |  |  |  |  | 2036-06-19 |  |  |  |  | 2036-06-26 |  |  |  |  | 2036-07-03 |  |  |  |  | 2036-07-10 |  |  |  |  | 2036-07-17
| House Remodel | 2035-09-21 | 2035-06-01 | -111 |  | 1% |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
High | Preconstruction | 2035-09-21 | 2035-10-02 | 12 |  | 46%
Medium | Final Estimate Complete | 2035-09-21 | 2035-09-21 | 1 | Complete | 100% | Name
Low | Contract Signed | 2035-09-22 | 2035-09-29 | 8 | Complete | 100% | Name
Medium | Permission to Schedule Work? | 2035-10-02 | 2035-10-02 | 1 | In Progress | 40%
Medium | Demo Prep |  |  | 1 |  | 0%
Medium | Appliance, Fixture, and Salvage |  |  | 1 | Complete | 100%
High | Electrical - Cut Power and Install Temp Service |  |  | 1 | Not Started | 0%
High | Safety Fence Delivery/Setup |  |  | 1 | In Progress | 30%
High | Install Office/Safety Area (Plans Desk, First Aid, Phone) |  |  | 1 |  | 0%
| Install Site Camera(s) |  |  | 1 |  | 0%
| Demolition |  |  | 1 |  | 0%
| Scrap the Upper Two Floors |  |  | 1 |  | 0%
| Basement Demolition |  |  | 1 |  | 0%
| Excavation |  |  | 1
| Foundation Prep |  |  | 1
| Oil Tanks |  |  | 1
| Backfill |  |  | 1
| Concrete |  |  | 1
| Footings, Walls, and Pads |  |  | 1
| Slabs |  |  | 1
| Pre Backfill |  |  | 1
| Drainage |  |  | 1
| Waterproofing |  |  | 1
| Framing |  |  | 1
| Level/True Basement and Main Floor |  |  | 1
| Frame New Home and Addition |  |  | 1
| Roof |  |  | 1
| Dry In Roof - IWS and Felt |  |  | 1
| Upper Roofing |  |  | 1
| Flat Roofs |  |  | 1
| Plumbing |  |  | 1
| Ground Work |  |  | 1
| Rough In |  |  | 1
| Windows |  |  | 1
| Order Windows |  |  | 1
| Wrap Sills |  |  | 1
| Install Windows |  |  | 1
| HVAC |  |  | 1
| Ducting and Gas Piping |  |  | 1
| Fire System for Drywall |  |  | 1
| Electrical |  |  | 1
| Electrical - Rough In |  |  | 1
| Walkthrough |  |  | 1
| A/V |  |  | 1
| Low Voltage - CATV, CAT6, Tele |  |  | 1
| Speaker Pre-Wire |  |  | 1
| Alarm/Security Wiring |  |  | 1
| House Wrap |  |  | 1
| House Wrap |  |  | 1
| Insulation |  |  | 1
| Blow In |  |  | 1
| Bats |  |  | 1
| Rigid |  |  | 1
| Drywall |  |  | 1
| Delivery |  |  | 1
| Hang and Scrap |  |  | 1
| Tape |  |  | 1
| Prime |  |  | 1
| Touch Up If Needed |  |  | 1
| Exterior Stone |  |  | 1
| Back Patio |  |  | 1
| Back Entry |  |  | 1
| Exterior Case Work |  |  | 1
| Trim Windows |  |  | 1
| Siding |  |  | 1
| Laundry/Furnace Room Flooring |  |  | 1
| Install and Stay Off |  |  | 1
| Hardwoods |  |  | 1
| Deliver/Acclimate |  |  | 1
| Install Hardwoods |  |  | 1
| Stain |  |  | 1
| Finish |  |  | 1
| Cure and Protect |  |  | 1
| Tile |  |  | 1
| Prep |  |  | 1
| Install |  |  | 1
| Install |  |  | 1
| Cabinets |  |  | 1
| Master Bath |  |  | 1
| Upper Floor Bathrooms |  |  | 1
| Kids' Built-Ins |  |  | 1
| Upper Floor Built Ins |  |  | 1
| Kitchen |  |  | 1
| Main Floor |  |  | 1
| Basement |  |  | 1
| Plumbing Hang Sinks |  |  | 1
| Install under Mount Sinks |  |  | 1
| Interior Doors |  |  | 1
| Delivery-Hang |  |  | 1
| Ship to Pre-Fin |  |  | 1
| Millwork |  |  | 1
| Millwork Material Delivery |  |  | 1
| Millwork Install |  |  | 1
| Interior Painting |  |  | 1
| Millwork Prep |  |  | 1
| Cleaning and Masking |  |  | 1
| Millwork Painting and Curing (Oil) |  |  | 1
| Interior Walls and Ceilings |  |  | 1
| Stone Counters |  |  | 1
| Templating |  |  | 1
| Install |  |  | 1
| Schedule Buffer |  |  | 1
| Decks |  |  | 1
| Decking |  |  | 1
| Railings |  |  | 1
| Interior Doors Hang and Hardware |  |  | 1
| Return from Pre-Fin Shop |  |  | 1
| Hang |  |  | 1
| Install Hardware |  |  | 1
| Appliances |  |  | 1
| Delivery |  |  | 1
| Install |  |  | 1
| Plumbing |  |  | 1
| Set Toilets, Sinks, etc. |  |  | 1
| Electrical |  |  | 1
| Trim Cans |  |  | 1
| Outlets and Switches |  |  | 1
| Surface Mount Fixtures |  |  | 1
| Bathroom Glass |  |  | 1
| Mirrors |  |  | 1
| Shower Doors |  |  | 1
| Garage Door Dress Up |  |  | 1
| Final Inspections |  |  | 1
| Plumbing, Electrical, Mechanical |  |  | 1
| Final Inspection |  |  | 1
| Wrap Up |  |  | 1
| Punch List and Touch Up |  |  | 1
| Bath Accessories |  |  | 1
| Remove Tools |  |  | 1
| Remove Materials |  |  | 1
| Deliver Job Book (Sub List, Warranty/Install Paperwork, etc.) |  |  | 1
| Deliver Keys and Garage Remotes |  |  | 1
| House Cleaning |  |  | 1
| Yard |  |  | 1
| Home |  |  | 1
| Garage |  |  | 1
| Windows |  |  | 1
| Complete | 2035-06-01 | 2035-06-01 | 1
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2035-09-20 M to 2035-09-20 W
Formulas:
Project Manager = [Project Manager, row below]
TODAY

## Dropdown Key - Do Not Delete
PRIORITY | STATUS
Low | Not Started
Medium | In Progress
High | Complete

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.