## Project-Based IT Budget
Project-Based IT Budget Template
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
1.0 | PROJECT 1: Cloud Migration
1.1 | Planning & Architecture | Not Started |  |  |  | 5 | 50 | 250 | 5000 | 0.03 | 150 |  |  |  |  | 0 | 800 | 400 | 400
1.2 | Procurement (Licensing, Cloud Services) | In Progress |  |  |  | 25 | 35 | 875 |  |  | 0 |  |  |  |  | 0 | 1000 | 875 | 125
1.3 | Setup & Configuration | Complete |  |  |  | 40 | 75 | 3000 | 1 | 2600 | 2600 |  |  |  |  | 0 | 6000 | 5600 | 400
1.3a | Security & Compliance | Needs Review | [5 empty] | 0 |  |  | 0 |  | 5200 |  |  | 5200 | 5000 | 5200 | -200
1.3b | Testing & QA | Approved | [5 empty] | 0 |  |  | 0 |  |  | 4000 |  | 4000 | 4000 | 4000 | 0
1.3c | Go Live | Overdue | [5 empty] | 0 |  |  | 0 |  |  |  | 1600 | 1600 | 500 | 1600 | -1100
1.3d | Post-Migration Support | Not Started | [5 empty] | 0 |  |  | 0 |  | 3200 |  |  | 3200 | 2500 | 3200 | -700
1.4 | Task | Not Started | [5 empty] | 0 | 5 | 350 | 1750 |  |  |  |  | 0 | 1500 | 1750 | -250
1.5 | Task | Not Started |  |  |  | 17 | 85 | 1445 |  |  | 0 |  |  |  |  | 0 | 2000 | 1445 | 555
[8 empty] | 5570 |  |  | 4500 | 0 | 8400 | 4000 | 1600 | 14000 | 23300 | 24070 | -770
[6 empty] | LABOR |  |  | MATERIALS |  |  | OTHER |  |  |  |  | BUDGET vs. ACTUAL |  | BALANCE
TASK ID | DESCRIPTION | STATUS | START DATE – PLANNED – | START DATE – ACTUAL – | END DATE | HOURS | $ / HR | LABOR TOTAL | UNITS | $ / UNITS | MATERIALS TOTAL | TRAVEL | EQUIP. / SPACE | FIXED | MISC. | OTHER TOTAL | BUDGET | ACTUAL | UNDER / OVER
2.0 | PROJECT 2: Network Upgrade
2.1 | Infrastructure Procurement | Not Started | [5 empty] | 0 | 15 | 480 | 7200 |  |  |  |  | 0 | 8500 | 7200 | 1300
2.2 | Cabling & Hardware Setup | On Hold | [5 empty] | 0 |  |  | 0 | 1800 |  |  |  | 1800 | 2200 | 1800 | 400
2.3 | Configuration & Integration | On Hold |  |  |  | 72 | 150 | 10800 |  |  | 0 |  |  |  |  | 0 | 14000 | 10800 | 3200
2.4 | Monitoring & Optimization | In Progress | [5 empty] | 0 |  |  | 0 |  |  |  | 1650 | 1650 | 2000 | 1650 | 350
2.5 | Task | Not Started | [5 empty] | 0 | 2 | 8000 | 16000 |  |  |  |  | 0 | 10000 | 16000 | -6000
2.6 | Task | Not Started | [5 empty] | 0 |  |  | 0 |  |  | 8600 |  | 8600 | 8600 | 8600 | 0
2.7 | Task | Not Started |  |  |  | 40 | 50 | 2000 |  |  | 0 |  |  |  |  | 0 | 3000 | 2000 | 1000
2.8 | Task | Not Started |  |  |  | 160 | 40 | 6400 |  |  | 0 |  |  |  |  | 0 | 7500 | 6400 | 1100
2.9 | Task | Not Started | [5 empty] | 0 |  |  | 0 |  | 14000 |  |  | 14000 | 18000 | 14000 | 4000
[8 empty] | 19200 |  |  | 23200 | 1800 | 14000 | 8600 | 1650 | 26050 | 73800 | 68450 | 5350
CLICK HERE TO CREATE IN SMARTSHEET

## Dropdown Keys - Do Not Delete
DROPDOWN KEYS
STATUS
Not Started
In Progress
Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.