## EXAMPLE - Agile Gantt
Agile Gantt Chart Template Example
Project Name |  |  |  | Start Date |  | Overall Progress |  | Project Deliverable
Product Release |  |  |  | 2025-09-02
Project Manager |  |  |  | End Date |  | 35% |  | Scope Statement
Krista Ahmed |  |  |  | 2025-10-10
At Risk | Task Name | Feature Type | Responsible | Story Points | Start | Finish | Duration in days | Status | Comments
No | Sprint 1 |  | Krista Ahmed |  | 2025-09-03 | 2025-09-13 | 11
No | Feature 1 |  | Leigh Gibbs |  | 2025-09-03 | 2025-09-07 | 5 | Complete
Yes | Feature 2 |  | Kiran Gupta |  | 2025-09-07 | 2025-09-12 | 6 | In Progress
No | Feature 3 |  | Kiran Gupta |  | 2025-09-09 | 2025-09-13 | 5 | Overdue
No | Sprint 2 |  | Kiran Gupta |  | 2025-09-16 | 2025-09-24 | 9
No | Feature 4 |  | Krista Ahmed |  | 2025-09-16 | 2025-09-17 | 2 | Approved
Yes | Feature 5 |  | Leigh Gibbs |  | 2025-09-17 | 2025-09-21 | 5 | Needs Review
No | Feature 6 |  | Makara McLean |  | 2025-09-22 | 2025-09-24 | 3 | On Hold
No | Sprint 3 |  | Makara McLean |  | 2025-09-24 | 2025-10-05 | 12
No | Feature 7 |  | Krista Ahmed |  | 2025-09-25 | 2025-09-29 | 5 | Not Started
No | Feature 8 |  | Hazel Christensen |  | 2025-09-24 | 2025-10-02 | 9 | Not Started
No | Feature 9 |  | Kiran Gupta |  | 2025-10-02 | 2025-10-05 | 4 | Not Started
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
Start = MIN([Start, row below]:G12)
Overall Progress = MAX([Overall Progress, row below]:H12)

## BLANK - Agile Gantt
Agile Gantt Chart Template
Project Name |  |  |  | Start Date |  | Overall Progress |  | Project Deliverable
Project Manager |  |  |  | End Date |  |  |  | Scope Statement
At Risk | Task Name | Feature Type | Responsible | Story Point | Start | Finish | Duration in days | Status | Comments
| Sprint 1 |  |  |  | 0 | 0 |  | Not Started
Feature 1
Feature 2
Feature 3
| Sprint 2 |  |  |  | 0 | 0
Feature 4
Feature 5
Feature 6
| Sprint 3 |  |  |  | 0 | 0
Feature 7
Feature 8
Feature 9
Formulas:
Start = MIN([Start, row below]:G11)
Overall Progress = MAX([Overall Progress, row below]:H11)
Double click Horizontal (Value) Axis to format Bound Minimum and Maximum settings under Axis Options.

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
Needs Review
Approved
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.