## EXAMPLE Construction Dashboard
Construction Project Dashboard Template Example
Project Name |  |  |  | Date | Project Status | % Complete
Project Alpha |  |  |  | MM/DD/YY | In Progress | 72%
Task Timeline
Dashboard Data
Task Table
Task Name | Assigned To | Start Date | End Date | Duration in days | Status | Priority | Comments
Demo Prep | Alex B. | 2024-01-02 | 2024-01-08 | 6 | Complete | Low
Demolition | Frank C. | 2024-01-04 | 2024-01-11 | 7 | Complete | Medium
Excavation | Jacob S. | 2024-01-07 | 2024-01-11 | 4 | Complete | High
Concrete | Jacob S. | 2024-01-10 | 2024-01-15 | 5 | Complete | Low
Pre backfill | Jacob S. | 2024-01-13 | 2024-01-20 | 7 | Complete | Medium
Framing | Alex B. | 2024-01-16 | 2024-01-29 | 13 | Overdue | Low
Roof | Frank C. | 2024-01-19 | 2024-02-01 | 13 | In Progress | Low
Plumbing | Kennedy K. | 2024-01-22 | 2024-02-09 | 18 | In Progress | Medium
Windows | Jacob S. | 2024-01-25 | 2024-02-05 | 11 | In Progress | Medium
HVAC | Alex B. | 2024-01-28 | 2024-02-06 | 9 | On Hold | High
Electrical | Kennedy K. | 2024-01-31 | 2024-02-02 | 2 | Not Started | High
Launch | Donald W. | 2024-02-03 | 2024-02-04 | 1 | Not Started | High
Task Status % |  |  |  | Budget
STATUS | COUNT | % |  | PLANNED | 80000
Not Started | 2 | 16.67% |  | ACTUAL | 50000
In Progress | 3 | 25%
Complete | 5 | 41.67%
Overdue | 1 | 8.333%
On Hold | 1 | 8.333%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 5
High | 4 | 33.33% |  | Actions | 2
Medium | 4 | 33.33% |  | Change Requests | 4
Low | 4 | 33.33%
| 0 | 0%
TOTAL | 12 | 100%
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK Construction Dashboard
Construction Project Dashboard Template
Project Name |  |  |  | Date | Project Status | % Complete
|  |  |  | MM/DD/YY | Not Started | 0% | Enter DASHBOARD DATA in the tables beginning at row 8. Dashboard graphics will automatically populate.
Task Timeline
Dashboard Data
Task Table
Task Name | Assigned To | Start Date | End Date | Duration in days | Status | Priority | Comments
Task 1 | Name |  |  | 0 | Complete | High
Task 2 |  |  |  | 0 | Complete | High
Task 3 |  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
|  |  |  | 0 | Complete | High
TASK STATUS % |  |  |  | BUDGET
STATUS | COUNT | % |  | PLANNED | 0
Not Started | 0 | 0% |  | ACTUAL | 0
In Progress | 0 | 0%
Complete | 12 | 100%
Overdue | 0 | 0%
On Hold | 0 | 0%
TOTAL | 12 | 100%
TASK PRIORITY % |  |  |  | PENDING ITEMS
PRIORITY | COUNT | % |  | Decisions | 0
High | 12 | 100% |  | Actions | 0
Medium | 0 | 0% |  | Change Requests | 0
Low | 0 | 0%
| 0 | 0%
TOTAL | 12 | 100%
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown keys - DO NOT DELETE
DROP DOWN KEYS - DO NOT DELETE
STATUS | PRIORITY
Not Started | High
In Progress | Medium
Complete | Low
Overdue
On Hold

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.