## EXAMPLE Product Launch Gantt
Product Launch Gantt Chart Template Example
PRODUCT LAUNCH PLAN |  |  |  | START DATE
Project Beta |  |  |  | 2025-03-31
Use "BLANK" version tab for additional Task listings and weeks. | [6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7
TASK NAME | STATUS | PRIORITY | TASK OWNER | START DATE | END DATE | # of Days | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16
PLANNING PHASE | Complete | HIGH |  | 2025-03-31 | 2025-04-17 | 14 | bar: 2025-03-31 to 2025-05-16
Market Requirements Definition | In Progress | MED |  | 2025-03-31 | 2025-04-03 | 4 | bar: 2025-03-31 to 2025-04-03
Business Case | On Hold | LOW |  | 2025-04-02 | 2025-04-13 | 8 | bar: 2025-04-02 to 2025-04-11
Launch Plan | Complete | HIGH |  | 2025-04-13 | 2025-04-17 | 4 | bar: 2025-04-14 to 2025-04-17
Target Metrics | Overdue | LOW |  | 2025-04-11 | 2025-04-11 | 1 | bar: 2025-04-11
SALES TOOLS | Needs Update | LOW |  | 2025-04-17 | 2025-04-25 | 7 | bar: 2025-03-31 to 2025-05-16
Prospect Presentation | Needs Review | MED |  | 2025-04-17 | 2025-04-23 | 5 | bar: 2025-04-17 to 2025-04-23
Demo | Complete | HIGH |  | 2025-04-24 | 2025-04-25 | 2 | bar: 2025-04-24 to 2025-04-25
Competitive Positioning | On Hold | HIGH |  | 2025-04-23 | 2025-04-25 | 3 | bar: 2025-04-23 to 2025-04-25
– FAQ sheet | In Progress | MED |  | 2025-04-23 | 2025-04-25 | 3 | bar: 2025-04-23 to 2025-04-25
PRODUCT MARKETING | In Progress | MED |  | 2025-04-14 | 2025-04-30 | 13 | bar: 2025-03-31 to 2025-05-16
Pricing Strategy | In Progress | HIGH |  | 2025-04-14 | 2025-04-18 | 5 | bar: 2025-04-14 to 2025-04-18
Product Positioning | Complete | LOW |  | 2025-04-15 | 2025-04-16 | 2 | bar: 2025-04-15 to 2025-04-16
– Define Audience | Complete | HIGH |  | 2025-04-17 | 2025-04-17 | 1 | bar: 2025-04-17
– Core Messaging | Complete | HIGH |  | 2025-04-21 | 2025-04-24 | 4 | bar: 2025-04-21 to 2025-04-24
– Executive Approval | Complete | MED |  | 2025-04-25 | 2025-04-30 | 4 | bar: 2025-04-25 to 2025-04-30
SOCIAL | Complete | HIGH |  | 2025-04-28 | 2025-05-01 | 4 | bar: 2025-03-31 to 2025-05-16
Define social media strategy | Complete | HIGH |  | 2025-04-28 | 2025-04-30 | 3 | bar: 2025-04-28 to 2025-04-30
Schedule social media posts | Complete | HIGH |  | 2025-04-29 | 2025-05-01 | 3 | bar: 2025-04-29 to 2025-05-01
PRODUCT RELEASE | Complete | HIGH |  | 2025-05-01 | 2025-05-16 | 12 | bar: 2025-03-31 to 2025-05-16
Alpha Release | Complete | HIGH |  | 2025-05-01 | 2025-05-01 | 1 | bar: 2025-05-01
Beta Release | Complete | HIGH |  | 2025-05-05 | 2025-05-05 | 1 | bar: 2025-05-05
V1 General Availability | Complete | HIGH |  | 2025-05-12 | 2025-05-12 | 1 | bar: 2025-05-12
R2 Press Event | Complete | HIGH |  | 2025-05-16 | 2025-05-16 | 1 | bar: 2025-05-16
CLICK HERE TO CREATE IN SMARTSHEET | bar: 2025-03-31 to 2025-05-02

## BLANK Product Launch Gantt
Product Launch Gantt Chart Template
PRODUCT LAUNCH PLAN |  |  |  | START DATE
Name |  |  |  | 2025-03-31 |  |  | <-- Enter initial Start Date to populate Timeline dates.
User to complete non-shaded cells only. | [6 empty] | Wk 1 |  |  |  |  | Wk 2 |  |  |  |  | Wk 3 |  |  |  |  | Wk 4 |  |  |  |  | Wk 5 |  |  |  |  | Wk 6 |  |  |  |  | Wk 7 |  |  |  |  | Wk 8 |  |  |  |  | Wk 9 |  |  |  |  | Wk 10 |  |  |  |  | Wk 11 |  |  |  |  | Wk 12 |  |  |  |  | Wk 13 |  |  |  |  | Wk 14 |  |  |  |  | Wk 15 |  |  |  |  | Wk 16 |  |  |  |  | Wk 17 |  |  |  |  | Wk 18 |  |  |  |  | Wk 19 |  |  |  |  | Wk 20
TASK NAME | STATUS | PRIORITY | TASK OWNER | START DATE | END DATE | # of Days | time axis 2025-03-31 to 2025-08-15
PLANNING PHASE |  |  |  | 0 | 0 | 0
Market Requirements Definition | [5 empty] | 0
Business Case | [5 empty] | 0
Launch Plan | [5 empty] | 0
Target Metrics | [5 empty] | 0
0
0
SALES TOOLS |  |  |  | 0 | 0 | 0
Prospect Presentation | [5 empty] | 0
Demo | [5 empty] | 0
Competitive Positioning | [5 empty] | 0
– FAQ sheet | [5 empty] | 0
0
0
PRODUCT MARKETING |  |  |  | 0 | 0 | 0
Pricing Strategy | [5 empty] | 0
Product Positioning | [5 empty] | 0
– Define Audience | [5 empty] | 0
– Core Messaging | [5 empty] | 0
– Executive Approval | [5 empty] | 0
0
SOCIAL |  |  |  | 0 | 0 | 0
Define social media strategy | [5 empty] | 0
Schedule social media posts | [5 empty] | 0
0
0
0
0
PRODUCT RELEASE |  |  |  | 0 | 0 | 0
Alpha Release | [5 empty] | 0
Beta Release | [5 empty] | 0
V1 General Availability | [5 empty] | 0
R2 Press Event | [5 empty] | 0
0
0

## Dropdown Keys - DO NOT DELETE
DROPDOWN KEYS - DO NOT DELETE
STATUS | PRIORITY
Not Started | LOW
In Progress | MED
Complete | HIGH
On Hold
Overdue
Needs Review
Needs Update

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.