## MA Integration Scorecard -EX
M&A INTEGRATION SCORECARD TEMPLATE
AS OF |  | $ IN
100 Days Post Close |  | ' 000s
COMPLETED BY |  | DATE COMPLETED
|  | 100 DAYS |  | 1 YEAR
FINANCIAL SYNERGIES | STATUS | ACTUAL | PLAN | ACTUAL | PLAN | STATUS KEY
Reduce Operating Costs by $25 Million | ON PLAN | 17000 | 15000 | 0 | 25000 | ON PLAN
Reduce SG&A Headcount Expenses by $500K | ON PLAN | 300 | 380 | 0 | 500 | SLIGHTLY UNDER PLAN
TOTAL FINANCIAL SYNERGIES | ON PLAN | 17300 | 15380 | 0 | 25500 | OFF PLAN
OPERATIONAL SYNERGIES | STATUS | ACTUAL | PLAN | ACTUAL | PLAN
Decrease Inventory by $150 Million | ON PLAN | 75000 | 80000 | 0 | 150000
Reduce Headcount by 250 FTE | SLIGHTLY UNDER PLAN | 9000 | 10000 | 0 | 16000
TOTAL OPERATIONAL SYNERGIES | SLIGHTLY UNDER PLAN | 84000 | 90000 | 0 | 166000
MARKET / CUSTOMER SYNERGIES | STATUS | ACTUAL | PLAN | ACTUAL | PLAN
>98% Retention of Key Customers | ON PLAN | 98% | 98% | – | 98%
Increase Market Share by 5% | OFF PLAN | -1% | 3% | – | 5%
Other |  | – | – | – | –
PROJECT | STATUS | ACTUAL | PLAN | ACTUAL | PLAN
Retain at least 93% of Key Employees | ON PLAN | 92% | 96% | – | 93%
100% of "Critical Path" Milestones are completed on time and within budget | SLIGHTLY UNDER PLAN | 90% | 100% | – | 100%
All Integration Teams follow the Project Governance Procedures with discipline | OFF PLAN | 95% | 100% | – | 100%
Stakeholders Rate Communications an average score of 4 / 5 on trust, timeliness, believability, and appropriateness | SLIGHTLY UNDER PLAN | 90% | 100% | – | 100%
Other |  | – | – | – | –
Other |  | – | – | – | –
CLICK HERE TO CREATE IN SMARTSHEET

## MA Integration Scorecard -BLANK
M&A INTEGRATION SCORECARD
AS OF |  | $ IN
COMPLETED BY |  | DATE COMPLETED
|  | 100 DAYS |  | 1 YEAR
FINANCIAL SYNERGIES | STATUS | ACTUAL | PLAN | ACTUAL | PLAN | STATUS KEY
Reduce Operating Costs by $30 Million |  | 0 | 0 | 0 | 0 | ON PLAN
Reduce SG&A Headcount Expenses by $150K |  | 0 | 0 | 0 | 0 | SLIGHTLY UNDER PLAN
TOTAL FINANCIAL SYNERGIES |  | 0 | 0 | 0 | 0 | OFF PLAN
OPERATIONAL SYNERGIES | STATUS | ACTUAL | PLAN | ACTUAL | PLAN
Decrease Inventory by $150 Million |  | 0 | 0 | 0 | 0
Reduce Headcount by 100 FTE |  | 0 | 0 | 0 | 0
TOTAL OPERATIONAL SYNERGIES |  | 0 | 0 | 0 | 0
MARKET / CUSTOMER SYNERGIES | STATUS | ACTUAL | PLAN | ACTUAL | PLAN
>98% Retention of Key Customers |  | – | – | – | –
Increase Market Share by 5% |  | – | – | – | –
Other |  | – | – | – | –
PROJECT | STATUS | ACTUAL | PLAN | ACTUAL | PLAN
Retain at least 95% of Key Employees |  | – | – | – | –
100% of "Critical Path" Milestones are completed on time and within budget |  | – | – | – | –
All Integration Teams follow the Project Governance Procedures with discipline |  | – | – | – | –
Stakeholders Rate Communications an average score of 4 / 5 on trust, timeliness, believability, and appropriateness |  | – | – | – | –
Other |  | – | – | – | –
Other |  | – | – | – | –

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.